## Sheet1
Ministry of Technology
Information & Communication Technology Agency of Sri Lanka
Approved Action Plan 2023
SN | Name of the Program/ Project | NPD # | Total Program/ Project Allocation (RS. Mn.) | Allocation for 2023 (RS. Mn) | Source of Funds | Date of Commencement as per the NPD document | Date of Completion | Cumulative Physical Progress up to 31.10.2022 (%) (ongoing Projects Only) | Year 2023 Quarterly Financial Targets (Rs Mn) |  |  |  | Year 2023 Quarterly Physical Targets (%) |  |  |  | Output Indicators (KPIs) | Quarterly Targets for Planned Outputs for 2023 (cumulative) |  |  |  | Key Outcomes Indicator | Implementation Responsibility
[9 empty] | Q 1 | Q 2 | Q 3 | Q 4 | Q 1 | Q 2 | Q 3 | Q 4 |  | Q1 | Q2 | Q3 | Q4
1.0 ICTA High Priority Projects
1 | Preparation of National Digital Transformation Policy and The National Digital Transformation Roadmap 2030 | - | 1.2 | 1.2 | GoSL | 2023.Mar | 2023.Dec | 0 | 0 | 0.4 | 0.5 | 0.3 | 20% | 40% | 70% | 100% | 1) National Digital Transformation Policy and Roadmap- 2030 completed by end of Q3 2023 | 20% | 60% | 100% |  | 80% of Gov organization adopted the policy framework by end of 2024 80% of the targets identified in the roadmap successfully completed by end of 2024 | Chanuka Wattegama
2 | Government Payment Services Platform (PAY.GOV.LK) | 2021/01/DG | 127 | 49.3 | GoSL | 2021.Sep | 2023.Dec | 10% | 0.5 | 5 | 18.6 | 25.2 | 15% | 25% | 60% | 100% | 1) PAY.GOV.LK Platform Completed by end of 2023 |  |  |  | 100% | × 10% annual reduction in payment processing time by end of 2024 × 80% of users satisfied with the improved payment solution by 2024 × 80% of the Government employees handling payments satisfied with the improved solution by 2024 × 10% annual increase in electronic transactions with the govt. organizations | Tharitha Taldena
[17 empty] | 2) 3 workshops Conducted targeting for the operational employees by end of 2023 |  |  |  | 3
[17 empty] | 3) API and Back End Application Completed for the initial 20 Government Organizations by end of 2024- 30% completed by end of 2023 |  |  |  | 30%
[17 empty] | 4) Roll out of the platform in 20 Gov. Organizations by end of 2024 (Phase 1)- 5 govt organizations completed by end of 2023 |  |  |  | 5
[17 empty] | 5) S&M for the years 2023 - 25 completed (Annual component) |  |  |  | 20%
[17 empty] | 6) Project Completion and Results Report /M&E Assessment (PAY.GOV.LK) Completed by end of 2024 - 15% Completed by end of 2023 |  |  |  | 15%
2.0 MoT Priority Projects
2.1 Digital Government
1 | Employee Trust Fund Management (ETF) System | 12 | 100 | 15.47 | GoSL | 2016.Mar | 2023.Dec | 93% | 3.6 | 7.6 | 2.84 | 1.43 | 95% | 96% | 97% | 98% | 1) Completed the ETF system addressing all identified CRs by end of 1st quarter 2023 | 100% |  |  |  | × 40% Reduction of Processing Time for ETF Payments by end of 2023 (improved internal efficiency) × 65% User staff Satisfied with the ETF Solution by end of 2023 (effectiveness) × 70% of the users of ETF services satisfied with the reliability and quality of the service obtains by end of 2023 | Tharitha Taldena Bhagya Kumarasinghe
[17 empty] | 2) Completed the OAT of the ETF Core System by end of 2nd Quarter 2023. | 75% | 100%
[17 empty] | 3) 50 User Staff of ETF Board Trained by end of 1st quarter 2023 (through on the job training) | 100%
[17 empty] | 4) Completed the support and maintenance component planned for the year 2023 |  |  | 12.5% | 25%
[17 empty] | 5) Project completion and results report completed (through the Independent M&E Consultancy Firm to be hired under M&E Project ) by the end of 2023 |  |  |  | 100%
2 | ICT Solution for Government Analyst's Department (GAD) | 30 | 40 | 21.19 | GoSL | 2016.Mar | 2023.Dec | 25% | 0 | 5.5 | 6 | 9.69 | 25% | 50% | 75% | 85% | 1) Digital Solution for GAD Completed and Successfully Installed by end of 2023 |  | 25% | 60% | 100% | × 10% Annual Time Reduction in Handing Cases by end of 2023 × 20% Annual Increase in Number of Cases Handled and Reports Produced by end of 2023 × 70% of the GAD Staff Satisfied with the ICT solution by end of 2023 | Tharitha Taldena Nilanka Karunarathna
[17 empty] | 2) 50 User Employees Trained by end of 2023 (through on the job training) |  |  |  | 50
3 | National Spatial Data Infrastructure (NSDI) - Phase II | 39 | 530 | 17 | GoSL | 2016.Feb | 2023.Dec | 90% | 0 | 0 | 13.5 | 3.5 | 82% | 85% | 87% | 90% | 1) NSDI Platform Completed by end of 2nd quarter 2022 (Already Completed) |  |  |  |  | × 30% of Organizations accepted that their decision making process improved through usage of NSDI by end of 2023 (improved organizational performance) × 30% of the intended user organizations accessed to sensitive data through the NSDI platform by end of 2023 × 30% of Organizations shared spatial data on NSDI system by end of 2023 × XX (tbd) of innovative and varied mobile apps developed by using the NSDI data through PPP | Tharitha Taldena Nilanka Karunarathna
[17 empty] | 2)7 Awareness Sessions on NSDI Conducted by end of 2023 |  |  |  | 7
[17 empty] | 3) NSDI Policy Document (Already Completed) - Cabinet Approval Received by Q1 2023 | 100%
[17 empty] | 4) NSDI Secretariats Established - as an Interim Arrangement 90% completed by end of 2023 |  |  |  | 90%
[17 empty] | 5) Data Standardization Process Completed for 5 Domains by end of 2023 (15 Domains by end of 2025) |  |  |  | 5
[17 empty] | 6) NSDI Business Model Finalized by end of 2024- 10% completed by end of 2023 |  |  |  | 10%
7) Application Developed for 5 National Shared Services by end of 2025
8) NSDI Secretariat Established (permanent arrangements) by end of 2025
9) NSDI Act Formulated by end of 2025
10) 30% of Central Spatial Data Acquisition Completed by end of 2025
[17 empty] | 11) License renewal completed for NSDI (Annual Component) |  |  | 100%
4 | eParliament | 63 | 185 | 36 | GoSL | 2017.Mar | 2023.Dec | 50% | 0 | 0 | 29 | 7 | 60% | 70% | 80% | 90% | 1) Completed Iteration 3 (i3) of the E-Parliament System Completed by end of 2023 |  | 50% | 70% | 100% | × 20% Increase in publishing documents /information electronically by end of 2023 × 25% of the Members accepted the timely delivery of information to members by 2023 (feedback from MPs to be collected by the Parliaments SG s office) × 10% Annual cost reduction in producing documents | Sameera Jayawardena
[17 empty] | 2) UAT and OAT Successfully Completed by end of 3rd quarter 2023 |  |  |  | 100%
3) S&M Completed for the period of 2023-24 (11 Mn)- annual components
5 | Sri Lanka Unique Digital Identity Framework Project (SL-UDI) | 2021/11/DG | 6635 | 876.3 | GoSL | 2021. Nov | 2025.Dec | 16% | 236.38 | 325.88 | 95.88 | 218.18 | 19% | 24% | 31% | 40% | 1) The Sri Lanka Unique Digital Identity ' Framework and related components completed by 2025- 30% completed by end of 2023 (Overall Project) |  | 5% | 15% | 30% | × 70% improve in the # of successful e-commerce related transactions by end of 2024 × 10% annual cost reduction in obtaining Govt services × 60% of the Citizens aware/educated of the importance of the Digital ID by end of 2025 × 60% of the Citizens satisfied with the Digital ID by end of 2024 × 40% Reduced costs in accessing gov. services by end of 2024 | Nilukshi Fonseka
[17 empty] | 2) Network Operating System (NOC) & Security Operating System (SOC) Completed by end of 2024- 70% completed by end of 2023 | 5% | 15% | 50% | 70%
[17 empty] | 3) The Media Campaign of SL-UDI completed by end of 2024 |  |  |  | 20%
[17 empty] | 4) 400 Government Staff - (Phase I) Trained for Handling Enrolment Process by end of 2025 |  |  |  | 40
[17 empty] | 5) 150 Enrolment Centers established Across the Country by end of 2024 (DRP)- 45 enrolment center s completed by end of 2023 |  |  |  | 45
|  |  | 3500 Grant | 23.8 | GOI | 2022.Mar | 2025.Dec | [9 empty] | 6) 2 Mn Digital IDs Issued by end of 2025 |  |  |  | -
6 | Government Digital Forms (Form.gov.lk) | NPD Approved under CERC | 87.8 | 15 | GoSL | 2020. Sep | 2023. Dec | 5% | 2.5 | 2 | 2.5 | 8 | 10% | 25% | 30% | 35% | 1) Established fully –pledged Forms.gov.lk platform by end of 2022 (already completed) | N/A | N/A | N/A | N/A | × 70% of the citizens using government services accepted that the service quality and reliability improved ( feed back collected from the relevant Govt. organizations) by end of 2023 × 10 % annual average reduction of paper usage by end of 2023 × 10 % annual average reduction of travel cost for the users of government services by end of 2023 | Tharitha Thaldena Kushan Perera
[17 empty] | 2) Roll-out & Operationalization of the Forms.gov.lk platform in 40 Government Organizations completed by end of 2023 | 25% | 50% | 75% | 100%
[17 empty] | 3) Trained intended users of the system (government officials) in periodic basis in 40 Government Organizations by end of 2024 | 25% | 50% | 75% | 100%
[17 empty] | 4) Conducted quarterly refresher training sessions | 25% | 50% | 75% | 100%
[17 empty] | 5) S&M Completed for the period of 2023-24 (annual components) | 25% | 50% | 75% | 100%
2.2 Digital Services
7 | Lanka Government Network 2.0- (Support and maintenance and handling change requests) | 1 | 12737.29 | 2354 | GoSL | 2016.Jun | 2023.Dec | 100% | 0 | 1900 | 223 | 231 | 25% | 50% | 75% | 100% | 1) Successfully completed the Support Maintenance for the Core Network and 860 End Sites up to end of 2023 component completed | 25% | 50% | 75% | 100% | × 60% reduction in communication cost in Govt. Organizations by end of 2023 × 70% of users satisfied with quality and reliability of LGN by end of 2023 × 70% of the Government employees with positive attitudes and behaviors on LGN usage by 2023 × 70% of intended users are effectively using the LGN facilities provided by 2023 | Kanchana Thudugala
[17 empty] | 2) Successfully complete Change Requests by end of 2023 | 25% | 50% | 75% | 100%
[17 empty] | 3) CRM and Ticketing System Operationalized by end of 2022\3, APNIC Payment | 25% | 50% | 75% | 100%
[17 empty] | 4) Provided Support and maintenance services of integrated Ticketing System and Call Center Application of Service Desk | 25% | 50% | 75% | 100%
[17 empty] | 5) Provided Support and Maintenance for Email-annual component | 25% | 50% | 75% | 100%
[17 empty] | 6) Site inspection and assists verification completed | 25% | 50% | 75% | 100%
8 | Lanka Government Cloud 2.0, Phase 02 enhancement | 86 | 2449.5 | 512 | GoSL | 2017.Mar | 2023.Dec | 70% | 132 | 83 | 196.4 | 100.6 | 77% | 82% | 87% | 100% | 1) Co-Location services provided for Lanka Government Cloud 2.0 - 25% completed by end of 2023 |  |  | 13% | 25% | x 20% reduction of cost for Digital Infrastructure and Maintenance through accessing Centrally Managed Cloud (LGC) Services by end of 2024 x 70% users satisfied with quality and reliability of LGC by end of 2024 x 70% of Gov. Organizations hosted Govt. data on the LGC by 2024 x 70% of Gov. Application Hosted in the LGC by 2023 | Ashok Cananathan Malith Galketiya
[17 empty] | 2) Virtual Web Application Firewall services provided for Lanka Government Cloud (LGC 2.0) |  | 75%
[17 empty] | 3) Red Hat OpenStack subscriptions obtained for Lanka Government Cloud (LGC 2.0) - 1 Year |  |  |  | 10%
[17 empty] | 4) Support and maintenance during the year 2023 for the LGC 2.0 Bare metal Servers completed. | 12.5% | 25% | 50% | 75%
[17 empty] | 5) Support Maintenance for the Redhat Open Stack provided. |  |  | 20% | 80%
[17 empty] | 6) Memory upgraded of Lanka Government Cloud (LGC) 2.0 | 100%
[17 empty] | 7) Automated Backup Solution completed by 3rd quarter 2023 (1 Year) | 25% | 50% | 100%
[17 empty] | 8) Enhanced LGC 2.0 Security Fabric | 25% | 100%
[17 empty] | 9) LGC 2.0 Staging Environment (for future upgrades) | 25% | 50% | 90% | 100%
2.3 Digital Economy
9 | Technology Industry Development Program | 2021/04/DE | 759 | 175 | GoSL | 2021.Sep | 2023.Dec | 12% | 20 | 30 | 50 | 75 | 13% | 20% | 30% | 40% | 1) Increased exports market readiness capacity in IT-BPM companies ( 112 Companies by end of 2024) **Original Cumulative Target for 2024 - 250 **Original Target for 2023 - 100 |  |  |  | 62 | × 3.0 Bn USD Foreign Exchange Revenue generated from IT-BPM Companies by end of 2024 × 100,000 New Jobs created from IT BPM Industry by end of 2024 × 700 IT BPM Companies in operation by end of 2024 (B/L in 2020- 400 companies) | Chiranthi Balapatabendi
[17 empty] | 2) Increased Re-skilled/ up-skilled IT-BPM workforce (Target of 237 Workforce by end of 2024) **Original Cumulative Target for 2024 - 1000 **Original Target for 2023 - 350 |  |  |  | 137
[17 empty] | 3) Increased international market access opportunities (92 Companies by end of 2024) **Original Cumulative Target for 2024 - 300 **Original Target for 2023 - 120 |  |  |  | 42
[17 empty] | 4) Findings/reports on Global market trends, export market analysis, IT-BPM industry development reports (08 market surveys / reports completed by end of 2024) **Original Cumulative Target for 2024 - 12 **Original Target for 2023 - 5 |  |  |  | 5
[17 empty] | 5) Increased female participation (%) in the IT-BPM workforce (Increase by 3% to achieve 37% by end of 2024) **Original Cumulative Target for 2024 - Increase by 11% to achieve 45% ** Original Target for 2023 - 3% |  |  |  | 1%
[17 empty] | 6) Increased Brain-gain in the IT-BPM workforce (30 individuals by end of 2024) **Original Cumulative Target for 2024 - 100 ** Original Target for 2023 - 30 |  |  |  | 10
[17 empty] | 7) Freelancers up-skilled to engage with the IT-BPM industry (Survey to be completed & 150 up-skilled by end of 2024) **Original Cumulative Target for 2024 - 500 **Original Target for 2023 - 150 |  |  |  | 50
[17 empty] | 8) Increased Global reach by positioning Sri Lanka as a sought out IT/BPM destination (qualified leads) 9 qualified leads by end of 2024 **Original Cumulative Target for 2024 - 70 Qualified Leads **Original Target for 2023 - 20 |  |  |  | 4
[17 empty] | 9) Increased no of potential journalists/influencers/company’s visiting Sri Lanka (28 Individuals/ Companies by end of 2024) **Original Cumulative Target for 2024 - 30 **Original Target for 2023 - 10 |  |  |  | 13
[17 empty] | 10) Establishment of 5 IT sector global MNC’s; |  |  |  | 1
10 | Start-up and Scale up Program | 2021/05/DE | 625 | 181 | GoSL | 2021.Sep | 2023.Dec | 40% | 20 | 45 | 75 | 41 | 49% | 55% | 67% | 75% | 1) Increased the market access opportunities for 100 companies by end of 2024. | 40 | 50 | 60 | 70 | × Improved Start-up Eco System - 1,000 Registered Start-ups by end of 2024 × 10% of the Annual Foreign Exchange Revenue generated (IT-BPM Sector) through start-ups by end of 2024 × 10% of the Start-up founders are female by end of 2024 × 10,000 of the Direct Employment Opportunities generated by end of 2024 | Sachindra Samararatne
[17 empty] | 2) Increased access to funds and availability of funds for 60 companies by end of 2024. | 20 | 26 | 32 | 40
[17 empty] | 3) Increased access to incubators/accelerators - 150 companies by end of 2024. | 25 | 45 | 85 | 120
[17 empty] | 4) Increased awareness on startup ecosystem and startup related knowledge areas - to 5000 participants by end of 2024. | 2000 | 2500 | 3000 | 3500
[17 empty] | 5) Increased initiatives to support 100 female founders by end of 2024. | 30 | 40 | 60 | 80
[17 empty] | 6) Increased talent access for 500 startups by end of 2024. | 50 | 100 | 150 | 200
11 | Entrepreneurship Promotion, Education and Incubation program | 2021/06/DE | 337.61 | 108.09 | GoSL | 2021.Sep | 2023.Dec | 7% | 10 | 30 | 38.09 | 30 | 26% | 32% | 50% | 60% | 1) 18 Tech Startup Newsletters published by end of 2024. | 1 | 2 | 4 | 6 | Outcomes × 10% of the 3Bn USD generated through Start-ups by end of 2024 Intermediate Outcomes × 1,000 New Business ideas incubated by end of 2024 × 20 New Active Incubators in Universities by end of 2024 | Sachindra Samararatne
[17 empty] | 2) Completed Support programs to refine business ideas to business plans | 7 | 10 | 15 | 20
[17 empty] | 3) Activity based entrepreneurship module is included in the national curriculum (Grade 9-11) _ Subject to be decided |  | 5% | 10% | 0.2
[17 empty] | 4) Accelerated new business ideas are registered with ROC | 15 | 35 | 55 | 80
[17 empty] | 5) Established incubators in universities |  | 1 | 2 | 4
12 | Technology Diffusion program | 2021/07/DE | 1002 | 178 | GoSL | 2021.Sep | 2023.Dec | 20% | 5 | 10 | 50 | 113 | 5% | 12% | 20% | 25% | 1) ICTA Innovation laboratories setup by end of 2024 |  | 1 | 3 | 5 | × 750 SMEs effectively adopted new and emerging technologies by end of 2024 × 60% effective adoption of the Government Policy on regulatory support to develop and adopt New Technologies | Sachindra Samararatne
[17 empty] | 2) ICTA GovTech Laboratories Setup by end of 2024 |  |  | 1 | 1
[17 empty] | 3) MNC sponsored Research and Development labs setup in universities by end of 2024 |  | 1 | 2.5 | 3
[17 empty] | 4) Local and international satellite campuses setup by end of 2024 |  | 0.5 | 1.5 | 1
[17 empty] | 5) Increased number of SMEs who successfully use technology adoptions to their core businesses by end of 2024 | 10 | 25 | 35 | 50
[17 empty] | 6) Increased number of non- technological start ups who use technologies by end of 2024 | 10 | 50 | 75 | 100
[17 empty] | 7) Set up Technology Diffusion Cells by end of 2024 |  | 1.25 | 1.75 | 2
[17 empty] | 8) Online market place with multiple services in place by end of 2024 |  | 45 | 65 | 85
[17 empty] | 9) Increased technical know-how among industries ( workshops/ seminars conducted by end of 2024) | 7 | 12 | 17 | 20
[17 empty] | 10) Tech diffusion forums / conferences conducted for 3000 participants by end of 2024 |  | 600 | 1200 | 1500
[17 empty] | 11) Prototyping facilities setup for Users by end of 2024 |  | 25 | 45 | 75
[17 empty] | 12) Digital Agriculture Strategy Formulation and Rollout completed by end of 2025 | 20% | 30% | 35% | 40%
13 | Capacity Building Component 1: Empowering citizens to adopt digital technologies | 2021/08/DE | 1055 | 273 | GoSL | 2021.Sep | 2023.Dec | 30% | 26.5 | 45.5 | 87 | 114 | 32% | 35% | 45% | 50% | Component 1 - Empowering citizens to adopt digital technologies
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 25%; Year 2023 Quarterly Physical Targets (%) Q 2: 35%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 1) Endorsed 5 D4E Citizen Apps by end of 2024 |  | 1 |  | 2 | × 75% of the Citizens digitally literate by end of 2024 × 70% of Citizens accessed and used digital services by end of 2024 | Sameera Jayawardene Kasun Tharaka
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 25%; Year 2023 Quarterly Physical Targets (%) Q 2: 35%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 2) 170 Boot Camps completed with 34,000 youth participation including marginalized groups for inducing the mindset on innovation and digital transformation. | 10 | 25 | 45 | 65
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 25%; Year 2023 Quarterly Physical Targets (%) Q 2: 35%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 3) 45 Training Workshops on Digital Helping Hands initiative successfully completed. | 3 | 7 | 12 | 15
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 25%; Year 2023 Quarterly Physical Targets (%) Q 2: 35%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 4) Successfully trained 20000 women through "Future Ready Women" program by end of 2024 | 5000 | 6000 | 7000 | 8000
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 25%; Year 2023 Quarterly Physical Targets (%) Q 2: 35%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 5) Integrated media campaign completed for citizens by end of 2024 | 1 | 1 | 2 | 2
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 25%; Year 2023 Quarterly Physical Targets (%) Q 2: 35%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 6) Improved utilization on user base citizen apps by end of 2024 (digital adoption) - Baseline to be established (% Increased from the Baseline) | 5% | 20% | 30% | 57.5%
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 25%; Year 2023 Quarterly Physical Targets (%) Q 2: 35%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 7) 2 D4E National Forums conducted by end of 2024 |  |  |  | 1
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 25%; Year 2023 Quarterly Physical Targets (%) Q 2: 35%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 8) National Freelancer drive-25 Regional Programs completed by end of 2024. | 3 | 8 | 12 | 15
| Capacity Building Component 2: Make future ready employable workforce | [15 empty] | Component 2 - Make future ready employable workforce
[17 empty] | 1) National Digital Education Policy and sector master plan launched by end of 1st Quarter 2023. 15% of Schools, Vocational Sector adopted masterplans by end of 2023 | 50% | 52% | 55% | 60% | × 75% of National Schools adopting Digital Education Policy by end of 2024 × 85% growth of students entering the IT faculties of Universities, Vocational & Higher Education Institutes by end of 2025 × 75% growth of students graduated from IT faculties of Universities, Vocational & Higher Education Institutes by end of 2024 × 80% of classrooms used appropriate technologies in the Teaching and Learning Process by end of 2024 × 300,000 IT Professionals available for workforce by end of 2024 | Sameera Jayawardene
2) Annual Digital Education Adoption Report completed by end of 2024
[17 empty] | 3) 15% National Skills Platform and adopted in Vocational Sector | 5% | 7% | 8% | 10%
[17 empty] | 4) Live and interactive network among educators, corporates, research communities and innovators created- 10 Networking events completed in 2024 | 1 | 3 | 5 | 7
[17 empty] | 5) 4750 IT Teachers trained as Master Trainers with the aim of transforming non-IT teachers (750 IT Master Trainers by end of 2024) | 100 | 500 | 1000 | 2750
[17 empty] | 6) Digitally skilled employ ready workforce produced from Universities, Vocational and Higher Education Sectors Institutions | 250 | 500 | 750 | 1000
[17 empty] | 7) National Workforce Survey Report published by end of 3rd quarter 2023 |  |  |  | 1
| Capacity Building: Component 3 - Improving capacities and digital competencies of Government employees | [15 empty] | Component 3 - Improving capacities and digital competencies of Government employees
[17 empty] | 1) Formulated Digital Government Maturity Model and adopted (500 organizations by end of 2025) | 5 | 15 | 30 | 50 | × 70% of the Government officials possessed with required digital competencies by end of 2024 × 300 Gov. Originations adopted the Maturity Model by end of 2024 × 500 CDIOs in Govt. Orgs. engaged with digital Government initiatives by end of 2024 × 60% of the Gov. Organizations Ranks Over 50% in the Maturity Model by end of 2024 | Sameera Jayawardene
2) Annual Digital Government Maturity Survey completed and report published
[17 empty] | 3) Required reforms to established Govt. ICT Service approved by the cabinet |  |  |  | 150
[17 empty] | 4) Government CDIO initiative - 500 Government CDIOs appointed and trained | 25 | 100 | 150 | 300
[17 empty] | 5) 500 gov. organizations to adopted the Digital Competency Framework | 25 | 100 | 150 | 300
[17 empty] | 6) Digital Government Capacity Building Need Assessment Survey completed for individuals | 4000 | 9000 | 14000 | 20000
[17 empty] | 7) 100,000 gov officers trained under the Next Gen Gov Officers initiative | 4000 | 5000 | 5000 | 20000
[17 empty] | 8) 200 Key Government Organizations deployed Government eLearning Platform | 5 | 15 | 25 | 50
[17 empty] | 9) Established 500 Digital Transformation Units in Govt. Organizations across the country | 25 | 100 | 150 | 300
[17 empty] | 10) Reform and adopt ICT service to Gov. org. | 0 | 5 | 50 | 150
[17 empty] | 11) Trained 2,600 Change Agents to implement Govt wide Change Management for digital Transformation. | 10 | 100 | 400 | 600
[17 empty] | 12) Partnerships with Development Agencies / Local or Foreign institutes to facilitate for a digital government transformation | 1 | 2 |  | 3
3.0 Other Approved Projects
3.1 Digital Government
1 | Government Web Development Platform_ (gov.lk Web Development Platform) | 2021/02/DG | 100 | 24.5 | GoSL | 2021.Sep | 2023.Dec | 10% | 0.5 | 0 | 10 | 14 | 12% | 15% | 70% | 100% | 1) Web Development Platform Completed by end of 2nd Quarter 2023 |  |  |  | 100% | × 80% of the citizens satisfied with the content and quality (user-friendliness etc.) of the websites × 80% of relevant Govt. organizations adopted the Standard Web Development Guidelines by end of 2023 × 25% Reduction of costs for govt. organizations web development by end of 2024 × 75% Increase in adoption of the Information Security Guidelines by end of 2024 | Tharitha Taldena Bhagya Kumarasinghe
[17 empty] | 2) 50 Gov. Officers Trained to use the web development platform by 2nd Quarter 2024- 25 officers trained by end of 2023 |  |  |  | 25
[17 empty] | 3) Developed 100 Government Websites Through the Web development Platform by end of 2024- web sites for 10 govt organizations are developed through the platform by end of 2023 |  |  |  | 10
4) 15 Capacity Building Sessions Conducted for 300 Government Organizations by end of 2024- For the purpose of effectively updating the website
[17 empty] | 5) Successfully Completed Maintenance of the Software Version of the Platform by end of 2025 |  |  |  | 50%
3.2 Digital Services
2 | Lanka Government Network 3.0 | Cabinet Approval to be Obtained |  | 781 | GOSL | 2023 | 2025 |  | 0 | 0 | 195 | 586 | 3% | 6% | 11% | 13% | 1) Cabinet Approval taken for the LGN 3.0 (improved version) | 50% | 100% |  |  |  | Kanchana Thudugala
[17 empty] | 2) LGN 3.0 implementation completed by end of 2024 | 5% | 15% | 30% | 50%
[17 empty] | 3) Infrastructure Transit/Migration to LGN 3.0- 30% completed by end of 2023 |  |  | 20% | 30%
[17 empty] | 4) 25 Promotional/Awareness Programs Conducted by end of 2023 |  | 25% | 50% | 100%
3 | Lanka Government Cloud 3.0 | Cabinet Approval to be obtained |  | 45 | GOSL | 2023 | 2025 |  | 0 | 15 | 15 | 15 | 3% | 6% | 11% | 13% | 1) Cabinet Approval taken for the LGC 3.0 (improved version)- by end of 2nd quarter 2023 | 50% | 100% |  |  |  | Ashok Cananathan Malith Galketiya
[17 empty] | 2) LGC 3.0 implementation completed by end of 2024 | 5% | 15% | 30% | 50%
[17 empty] | 3) Infrastructure Transit/Migration to LGC 3.0 |  |  | 20% | 50%
[17 empty] | 4) Promotional/Awareness Programs Conducted by end of 2023 |  | 25% | 100%
4 | Management and Operations of Government Information Centre (GIC) | 45 | 105.9 | 60 | GoSL | 2016.Feb | Annual Program - Ongoing Service Provision | 100% | 15 | 15 | 15 | 15 | 25% | 50% | 75% | 100% | 1) Knowledge Base Updated for 350 Government Institutions by end 2023 and subsequently annual updates up to 2024 | 5% | 15% | 30% | 50% | × 70% of the Citizens Accepted that they Receive Accurate and Reliable Information Through GIC by end of 2023 × Incoming calls received from both Sinhala and Tamil languages and from all the geographical areas – inclusiveness | Thilina Piyumal
[17 empty] | 2) GIC Routine Operations up to end of 2024 completed | 5% | 15% | 30% | 50%
3.3 Digital Economy
5 | Regional Cluster Development | 2021/09/DE | 163 | 56 | GoSL | 2021.Sep | 2023.Dec | 20% | 5 | 20 | 20 | 11 | 30% | 40% | 45% | 50% | 1) Established 5 Technology Diffusion Cells by end of 2024 across the country |  | 1 | 2 | 3 | × 10% annual increased of the Citizens using digital services in the region by end of 2024 × 10% annual increased IT related employment opportunities available in the regions by end of 2024 × 70% of beneficiaries of the regional clusters satisfied with the knowledge acquired through the regional knowledge hubs/ regional clusters by 2024 | Manoj Hemarathne Chadika Yahampath
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 2) Edu-tech platform for 3000 schools by end of 2024 (eThaksalawa Rollout) | 300 | 500 | 750 | 1,000 Schools
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 3) 5 knowledge and support hubs for clusters (one for each cluster by end of 2024- diffusion) |  | 1 | 2 | 3
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 4) Established Technology 5 educational Institutes by end of 2024 |  | 1 |  | 3
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 5) Improve soft skills of students in 100 educational organizations through Online education platform by end of 2024 (National Skills Framework) |  | 10 | 25 | 50
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 6) A special incentive schemes to 20,000 students for Higher education in the region by end of 2024 (Students Loan Scheme) | 2500 | 5000 | 10000 | 12500
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 7) 25 Startup Clinics created by end of 2024 | 3 | 5 | 10 | 15
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 8) Setting up a recognition platform (an annual event) to encourage/increase new innovations in the region by end of 2024. | 10% | 20% | 70% | 100%
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 9) Completed 5 Innovations Labs setup in the clusters by end of 2024 | 1 | 2 | 3 | 4
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 10) Established 7 start-up hubs by end of 2024 (Already established)
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 11) Decentralized potential tech companies (branches) in the regional clusters by end of 2024. |  |  |  | 1
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 12) Established 2 R & D Labs at regional clusters by end of 2024 (linking with universities). |  |  |  | 1
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 13) Establish 5 Tech based Incubators by end of 2024. |  | 1 | 2 | 3
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 14) Completed the Policy Document for Regional Clusters by end of 2024. | 5% | 20% | 35% | 50%
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 15) Improved partnership with the 50 Development Agencies, Non gov organizations, grassroots level organizations etc. (By end of 2024) | 5 | 10 | 20 | 25
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 16) Conducted 5 regional roadshows (Already Completed)
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 17) Regional Ecosystem Annual Assessment (25 Districts) |  |  |  | 25
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 18) Established 25 District Digital Transformation Committees by 1st quarter of 2023. | 10 | 25
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 19) Formulated 25 District Digital Transformation Roadmaps by 2nd quoter in 2023. |  | 25
[9 empty] | Year 2023 Quarterly Physical Targets (%) Q 1: 30%; Year 2023 Quarterly Physical Targets (%) Q 2: 40%; Year 2023 Quarterly Physical Targets (%) Q 3: 45%; Year 2023 Quarterly Physical Targets (%) Q 4: 50% | 20) Completed 10 Digital Hub District Expansion by end of 2024. |  |  | 2 | 3
3.4 Measuring Digital Transformation : Monitoring and Evaluation
6 | Implementation of Results Oriented Planning, Monitoring and Evaluation for digital transformation | 2021/10/CO | 198.84 | 19.6 | GoSL | 2021.Sep | 2023.Dec | 40% | 0 | 1 | 5 | 13.6 | 20% | 30% | 70% | 100% | 1) Conducted Monthly Project Progress Review Meetings | 3 | 6 | 8 | 12 | × 75% of the M&E Reports with Lessons Learned are Accepted by end of 2024 × 60% of Beneficiary Stakeholders Accepted that they have Opportunities in Taking Project Related Decisions Through M&E Findings by end of 2024 | Jagath Seneviratne Lochana Wijerathna Dhanusha Ariyasinghe
2)Independent M&E firm to gather outcome data available by end of Q1 2023 (Procurement process already completed)
[17 empty] | 3) Submitted quarterly monitoring reports through an independent M&E Consultant Firm in 2023 | 1 | 2 | 3 | 4
4) National Level and Project specific baseline and outcome assessments completed
[17 empty] | 5) M&E dashboard completed and updated by end of 2023 | 5% | 15% | 50% | 100%
[17 empty] | 6) 2 Workshops for lessons learned and formulate corrected actions completed. |  | 1 |  | 2
[17 empty] | 7) M&E Capacity Building Sessions conducted for ICTA internal staff |  | 1 |  | 2
[17 empty] | 8) Project proposals successfully completed and submitted to the NPD, adopting results based management approach. |  |  |  | 1
3.5 Strategic Communication for Digital Transformation
7 | Strategic Communication for Digital Transformation | 2021/13/CO | 170.775 | 56.15 | GoSL | 2021.Dec | 2023 Dec | 40% | 10.27 | 15.29 | 15.29 | 15.29 | 25% | 50% | 75% | 100% | 1) Mass Media Awareness Campaign - Completed for 2022 (30 TV Programs conducted by end of 2024) | 4 | 8 | 12 | 16 | × Increased Mass Awareness on digital technology adoption initiatives by end of 2024 (10% Annual Increase) × Increased understanding among journalist to report on the need for digital technology adoption by end of 2024 (10% Annual Increase) | Chanuka Wattegama
[17 empty] | 2) Mass Media Awareness Campaign (30 Print Media Articles done by end of 2024) | 2 | 4 | 6
[17 empty] | 3) Digital Media Awareness Campaign - Minimum 20 social media posts per month Published & 100,000 individuals reached Per Month) | 60 | 120 | 180 | 240
[17 empty] | 4) ICTA Website Revamped by end of 2022 |  |  |  | 100%
[17 empty] | 5) Public Relations (PR) Campaign Completed by end of 2024 (Minimum 4 Press Releases Per Month) | 12 | 24 | 36 | 48
[17 empty] | 6) Media Engagement for Journalists Completed by end of 2024 (10 Programs with the participation of 50 Journalists) |  | 3 |  | 6
[17 empty] | 7) ICTA Rebranding Campaign completed for 2023 and 2024 |  |  |  | 100%
[17 empty] | 8) Quarterly Digital Sri Lanka Magazine Published for 2022, 2023 & 2024 | 1 | 2 | 3 | 4
3.6 Policy for Digital Transformation; Digital Government and Digital Economy
8 | Policy for Digital Transformation; Digital Government and Digital Economy | Ministry Approved | 4.8 | 1.2 | GoSL | 2022.Jan | 2023.Dec | - | 0 | 0.2 | 0.4 | 0.6 | 20% | 40% | 70% | 100% | 1) Policy framework for Digital Platforms - Digital Economy/Industry Development completed by end of 2023 | 20% | 40% | 70% | 100% | × 75% of the Policies Effectively Adopted by end of 2024 | Chanuka Wattegama
[17 empty] | 2) Government Data Policy for Sri Lanka - Digital Government completed by end of 2023 | 20% | 40% | 70% | 100%
[17 empty] | 3) Digital Education Master Plan - Digital Economy/Capacity Development completed by end of 2023 | 20% | 40% | 70% | 100%
[17 empty] | 4) Digital Tax Policy Framework - Digital Economy/Industry Development completed by end of 2023 | 20% | 40% | 70% | 100%
[17 empty] | 5) Domestic Preferences Guidelines Preparation - Digital Government completed by end of 2023 | 20% | 40% | 70% | 100%
[17 empty] | 6) Policy Framework for Decentralized Finance - Digital Economy completed by end of 2023 | 20% | 40% | 70% | 100%
[17 empty] | 7) Guidelines for Online Transactions - Digital Government completed by end of 2023 | 20% | 40% | 70% | 100%
[17 empty] | 8) Other policy preparation tasks completed by end of 2023 (unspecified but based on need basis & requirements during the year 2023) | 20% | 40% | 70% | 100%