## 2020 Action Plan
Information and Communication Technology Agency of Sri Lanka Action Plan - 2020 ver 2.1 (2020.07.29)
# | Ref. No (NPD No) | Project Name | Description | Objectives | Activities planned for 2020 | Date of Commencement (NPD approved Date) | Date of Completion (originally planned) | Date of Completion (Extended period) | Total Budget Allocation as of NPD approval (Rs.mn) | Budget Allocation for 2020 (Rs.mn) | Considering the entire project period, please indicate planned percentage to be completed in each year (Total should be 100% by end of the project period). Physical progress is measured against project outputs (% achieved out of 100) |  |  |  | Financial Targets (%) in 2020 (Cumulative) in Rs. Mn |  |  |  | Physical Targets (%) in 2020 (Cumulative From the planned activities for 2020 |  |  |  | M&E arrangement |  |  |  |  | Responsible by (Program Manager) | Remarks
[23 empty] | Key Outputs | Key Outcomes | KPIs/OUTPUT and OUTCOME infdicators | Data Collection Method and Frequency | M&E Responsibility
Please refer the note below
[11 empty] | Actual Progress made in 2016 | Actual Progress made in 2017 | Actual Progress made in 2018 | Actual Progress made in 2019
[15 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | 1 | Lanka Government Network 2.0 | Building a centrally managed government network to link government institutions to a single digital infrastructure. | To improve efficiency & effectiveness of government service delivery process, and inter- governmental data sharing for delivering integrated services through establishing high speed, realiable Wide Area Network connectivity in government organizations To improve access to government services for all employees and citizens who are visiting to govt Organizations through Wi-Fi facilities . To ensure secure and reliable services through effectively carrying out operations and maintenance activities of the Lanka Government Network 2.0 . | Completed activities as to 31 December 2019: 1. LGN Core and Services including Firewall Management, Wireless Network Management, User Authentications, Network Management and Monitoring were established and operational of all established 860 sites. 2. All 860 sites are connected with the last mile connectivity up to 100Mbp and Wi-Fi facilities and increased Internet bandwidth from 2 Gbps to 10 Gbps 3. The LGII ticking system has established and operational | 2016.June | 2018.Dec | 2022.Dec | 4110.91 | 1877.05 | 34% | 36% | 27% | 3% (100% of the planned output of the project have been completed by the end of year 2019) Refer the note in Remarks column | 0 | 43.66 | 1297.1 | 395.3 | 110% | 120% | 130% | 150% | 1) 860 Government organizations are connected (up to 100Mbps last mile connectivity and Wi-Fi facilities) 2) Improved awareness, skills, knowledge on LGN facility- awareness sessions, training interned LGN User employees 3) Produced quarterly progress reports. 4) Effectively delivered and maintained the LGN services | Final Outcomes 1) Annual Reduction in time taken to obtain government services 2) Annual reduction of organizational operational/admin costs 3) Annual reduction of communication cost in govt organizations Intermediate Outcomes 1) Government officers aware about the benefit of LGN 2.0. 2) Government officers with positive attitudes and behavior on LGN usage. 3) Government officials effectively use LGN 2.0. | Output indicators 1) 860 Government organizations are connected (up to 100Mbps last mile connectivity and Wi-Fi facilities) by August 2018 2) Improved awareness, skills, knowledge on LGN facility- 11 awareness sessions, training 1500 interned LGN User employees 3) Produced quarterly progress reports. 4) Effectively delivered and maintained the LGN services Intermediate Outcomes indicators 1) At least 60% of surveyed government officers aware about the benefit of LGN 2.0 by December 2020. 2) At least 50% of surveyed government officers with positive attitudes and behavior on LGN usage by December 2020 3) At least 40% of government officials effectively use LGN 2.0 by end of 2020 Final Outcome indicators 1) 20% annual Reduction in time taken to obtain government services 2) 10% of annual reduction of organizational operational/admin costs 3) 10% annual reduction of communication cost in govt organizations | Regular M&E assessment on system usage (Real Time) - Monthly Reporting Rapid Assessment of LGN intermediate outcomes - Quarterly Reporting Periodical surveys to assess final outcomes - Annually | CTA M&E Team (Rutine M&E Data) outcome assesments - independent M&E consultants under the supervision of the ICTA M&E Head by annual surbey - indipendent outsourced firm | Ravindra Pathirana | As originally planned outputs of the project have already been completed, During 2020, more attention will be paid towards; - Establish an operational model for effective/ efficient operation and maintenance of the network - Promoting adoption and increase usage of LGN facility and - Include new application and services to improve service delivery process of entire government -Expand existing LGN coverage to adjacent buildings.
Planned activities for 2020: 1) Finalize the operational model of the LGN 2.0 after ending the contract period (from Oct-20 onwards) 2)Connecting Adjacent building of existing LGN sites 3) Provide LGN connectivity to new organizations 4) Carryout ongoing M&E activities 5) Conduct independent Outcome Evaluation 6) Prepare Project Completion Report 7) Improve adoption among intended users 8) Dismantle of LGN 1.0
2 | 3 | Lanka Government Cloud (LGC) 2.0 - Phase 1 (LGC2.0 Phase 1 Maintenance +LGC 1.0 maintenance) | To improve efficiency and effectiveness of government organizations through eliminating requirements of individual organization specific server facilities by establishing centrally manage secure and reliable cloud infrastructure/ solutions | 1) To provide reliable, secure and cost-effective cloud services 2) To promote effective utilization of hardware resources by adopting hybrid cloud model. 3) To provide centralized solutions for common platforms. 4) To align LGC 2.0 with the current technology to facilitate emerging needs. 5) To stop co-location payments of LGC 1.0 migrating all apps to LGC 2.0 | Completed activities as at 31 December 2019: The improved and industry standard version of Lanka Government Cloud 2.0 (LGC 2.0) has been established and is in live since August 2018. All e-Gov applications implemented by ICTA in LGC are connected to government organisations, which has improved the G2G communication between government organisations. Planned activities in 2020: 1) Provide Bare-Metal Server Facilities for General Cluster of Lanka Government Cloud 2.0 2) Provide Bare-Metal Server Facilities for Big-Data Cluster of Lanka Government Cloud 2.0 3) Provide for Co-location Services for Lanka Government Cloud 2.0 4) Installation, Configuration and Maintenance of Application Stacks for the Lanka Government Cloud 2.0 5) Mesosphere (Datacenter Operating System) Software License Subscriptions 6) Extension of the contract for LGC 2.0 and LGN 1.0 VPN links 7) Migrate all applications hosted in LGC 1.0 to LGC 2.0 8) LGC 1.0 Switch off and Dismantle | 2016.Mar | 2018.Dec | 2019.Dec | 621.7 | 194.05 | 55% | 9% | 31% | 10% (100% of the project outputs have been completed by the end of year 2019 ) | 32.6062 | 68.111 | 42.7702 | 38.0758 | 0% | 110% | 130% | 150% | 1) Established successfully operational of centralized Cloud LGC (2.0) - 24X7X365 & 99% availability and Improved reliability and consistency than in-house infrastructure 2) Organisations hosted their applications/eServices in centralized LGC 2.0 | 1) Organization wise cost reduction comparing with the cost incurred for in-house infrastructure management 2) Satisfied users with the quality & reliability of the services of LGC 2.0 3) Organizations hosting their data in the cloud 2.0 facility | Output indicators 1) Successfully operational of centralized Cloud LGC (2.0) established by August 2018 - 24X7X365 & 99% availability and Improved reliability and consistency than in-house infrastructure 2) # of organisations hosted their applications/eServices in centralized LGC 2.0 by Dec 2020 Outcome indicators 1) Organization wise cost reduction comparing with the cost incurred for in-house infrastructure management (Target : TBD) 2) at least 70 % of the users satisfied with the quality & reliability of the services by December 2020 3) # of organizations hosting their data in the cloud 2.0 facility | Regular M&E assessment on Cloud 2.0 usage - Monthly Reporting Rapid appraisal/ field visits to assess intermediate outcomes - Quarterly Reporting Periodical survey (annual) | CTA M&E Team (Rutine M&E Data) outcome assesments - independent M&E consultants under the supervision of the ICTA M&E Head by annual surbey - indipendent outsourced firm | Ravindra Pathirana | NPD Approval is required for 2020 Entire project outputs have been achieved. During 2020, mainly focuses the achievements of project outcomes (Ex- Increase the usage of the infrastructure and reduce the government cost.
[15 empty] | 32.6062 | 68.111 | 42.7702 | 38.0758
3 | 12 | Employee Trust Fund Management (ETF) System | Improve efficiency and effectiveness of the ETF system through implementing a consolidated centralized solution for the management of EPF / ETF funds (Develop an ICT solution for the Employee Trust Fund Board (ETFB) fund management system and related services, to offer efficient services to stakeholder organizations) | 1) To develop Employee Trust Fund Board (ETFB) Fund Management System. 2) To integrate key systems to enable (a) ETFB to verify online selected information when offering services to their clients, and to facilitate of stakeholder organizations. 3) Increase efficiency and effectiveness of functions and services of ETFB. 4) To increase member contributions. 5) To increase non-contributory benefit to employees on retirement. | Completed activities as of 31 December 2019: 1. Completed 100% of the Business Process Improvement (BPI) study report and reviewing of BPI. 2. Completed 100% of procurement process to hire a consultancy firm to develop ETF core system - completed inception report (1st deliverable) and requirement gathering process (2nd deliverable). 3. Development of ETF Core System Planned activities for 2020: 1. Hardware Devices and Supporting Software tools | 2016.Mar | 2018.Dec | 2020.Dec | 100 | 52.44 | 2% | 48% | 10% | 7% | 12.16 | 0 | 13.06 | 10 | 0% | 60% | 65% | 70% | 1) Established member centric ETF core system for the ETFB. 2) Trained employees under change management programs. 3) Trained intended officials. | 1) Improved convenience to the members in accessing all ETF related Services electronically. 2) Improved country position of the doing business index Intermediate outcomes 1) Improved usage of the system 2) Improved awareness and positive attitudes of intender users of the system/ ownership is created | Output indicators 1) % of Established member centric ETF core system for the ETFB (Target: 100% by October 2021) 2) User employees trained under change management programs (Target : 50 Users by end of 2020) 3) 100 intended officials are trained by mid 2021 Outcome indicators 1) % of convenience inproved when members in accessing all ETF related Services electronically. 2) Position of the country in doing business index 3) % of usage of the system 4) % of satisfaction of intender users of the system/ ownership | Quaterly basis M&E assesments on the system usage, employee satisfaction etc Periodical surveys to assess final outcomes - Annually Participants’ feedback, Workshop evaluation Project admin reportsbi annula evaluation under e Gov Outcome Evaluation rvey | ICTA M&E Team (Rutine M&E Data) outcome assesments - independent M&E consultants under the supervision of the ICTA M&E Head by annual surbey - indipendent outsourced firm | Gavashkar Subramanium
4 | 13 | Integrated Welfare management System (IWMS) | Develop a Single window for Sri Lanka Safety Net Management system. | 1) To improve effectiveness and efficiency in the management and provisioning of social welfare and subsidy management programs through establishing integrated welfare management systems 2) To improve management and delivery of social welfare and subsidies. 3) To develop a one stop shop for integrated welfare and subsidy management programs 4) To integrate subsidy management related citizen services 5) To Integrate the eSamurdhi system with population registry 6) To Integration of eSamurdhi with Beneficiary evaluation and subsidy management solution | Completed activities as of 31 December 2019: Completed the social registry Integrated system up to Iteration 2. Handing over of the project is in progress as Welfare Benefit Board has requested to handover with the completion of Iteration 2. Currently, a function and security audit is being carried out by an independent party and system is being improved according to the audit report. Planned activities for 2020: 1) Complete the knowledge transfer 2) Enhancement of IWMS System - ( CR) 3) Conduct UAT Signoff | 2016.Mar | 2018.Dec | 2020.Dec | 164 | 13.66 | 19% | 37% | 23% | 11% | 0 | 4.497 | 9.163 | 0 | 91% | 94% | 100% |  | 1) Developed the Integrated Welfare Management system (IWMS) 2) Completed the Social registry populated with current data on all beneficiary households of programs under the Welfare Benefit Scheme 3) Prepared the Eligibility criteria for selecting Welfare Benefit Scheme beneficiaries 4) Conducted training programs for Social Registry Units of DS divisions | 1) Improved efficiency and productivity in the management and provisioning of social welfare management 2) Eligible individuals forte welfare scheeame are properly identified | Output indicators 1) Integrated Welfare Management system (IWMS) is developed by July 2019 2) completion of Social registry populated with current data on all beneficiary households of programs under the Welfare Benefit Scheme by July 2019 3) Eligibility criteria prepared for selecting Welfare Benefit Scheme beneficiaries 4) Training programs conducted for Social Registry Units of DS divisions by July 2018 Outcome indicators 1) % of Improved efficiency and productivity in the management and provisioning of social welfare management 2) # of Eligible individuals forte welfare scheeame are properly identified | Rapid assessment in achieving intended intermediate outcomes - Quarterly Periodical surveys to assess final outcomes - Annually - bi annual e Gov Outcome evaluatyion survey | CTA M&E Team (Rutine M&E Data) outcome assesments - independent M&E consultants under the supervision of the ICTA M&E Head by annual surbey - indipendent outsourced firm | Kanchana Thudugala
5 | 14 | eLocal Government Programme | Enhance all citizen services provided by local government bodies and ensure proper security and audit policies. Envisages developing and implementing an ICT based solution which can be freely deployed at all (Local Govt Authorities) LAA to meet their generic requirements in providing citizen services- Support & Maintenance, eLocal Government-phase II, Project Management & Infrastructure | 1) Increasing the efficiency and effectiveness in governance, service delivery process, streamline internal management as well as promoting effective service delivery process. 2) Assure citizen friendly delivery of services by Improving social accountability and transparency 3) Enhance social inclusiveness and access to opportunities – Citizen are able to provide feedback on services offered in terms of quality and also to provide feedback on development needs of the area as well. 4) Strengthen the revenue base of the LAA 5) Encourage participatory good governance 6) Improved management in socio-economic development orientations | Completion of eLG - LPOPP integration | 2016.Mar | 2018.Dec |  | 1309 | 3.1 |  |  | 19% | ** Refer the note in Remarks column | 0.017 | 0 | 0.3 | 4.49 |  | 20% | 50% | 81% | 1) Deployed the eLG enhanced system for Local Authorities. 2) Completed the technical review of the existing eLG system 3) Completed the case study on the previous system to understand what worked and what didn't work | 1) Reduction of time taken to pay assessment tax to LAA 2) Improved convenience of tax payers 3) Improved internal efficiency of the LG organization | Output indicators 1) # of Local Authorities deployed the eLG enhanced system (Target - 10 Local Authorities) 2) % of completion of the technical review of the existing eLG system 3) % of completion of the case study on the previous system to understand what worked and what didn't work Outcome indicators 1) Reduction of time taken to pay assessment tax to LAA (at last 15% annual cost reduction) 2) Improved convenience of tax payers - at least 70% of tax payers satisfied with the quality of the service provide by end of 2023 3) Improved internal efficiency of the LG organization ( 10% annual cost reduction of operational and admin cost | Regular M&E assessment on eLocal Government Programme. - Monthly Reporting Rapid assessment in achieving intended intermediate outcomes - Quarterly Periodical surveys to assess final outcomes efficiency - Annually | ICTA M&E Team (Rutine M&E Data) outcome assesments - independent M&E consultants under the supervision of the ICTA M&E Head by annual surbey - indipendent outsourced firm | Shriyananda Rathnayake | The Board of ICTA yet to be decided on this project continuation / way forward in 2020
6 | 22 | Implementation of Gov.lk “Single Window” for Cross Government (Cluster implementation) | Intend to commence an initiative focuses on providing government services, integration with key cluster organizations and offered via a single window. The Imports and export cluster includes organizations such as Inland Revenue, Registrar of Companies and other stakeholder organizations; including recommending organizations for controlled items; such as Department of Excise, TRC, National Ozone Unit, Drugs Regulatory Authority, etc. | 1) To Implement a single window solution for the import and export cluster | Completed activities as of 31 December 2019: Established an internal Network infrastructure for the Import and Export Control. Further facilitated the development and launch of the online license issuing services through the Eservices development project. Manage the selected core components of the Gov.lk middleware infrastructure and common services such s GovSMS, Payment services and data exchange through an external technical consultant. Activities planned for 2020: 1) Continue managing the middlware infrastructure and common services 2) Transfer the responsibility of maintaining the online license issuance service to the ICTA technology team. 3) Technology upgrade and transfer the online services to the Lanka Government cloud 2.0 4) Ongoing discussions to implement the Import and Export Control backend application | 2016 Feb | 2018.Dec | 2020.Dec | 200 | 1.5 | 2% | 0% | 0% | 8% | 0.295 | 0.48 | 0.93 | 0 | 36% | 50% | 75% | 100% | 1) Facilitated for establishment of the online License Issuance service for importers and exporters 2) Established internal network at Import and Export Control 3) Managed Gov.lk middleware infrastructure and common services 4) Established back-end application at the import and export control department | 1) Improved efficiency in government services delivery 2) Improved government revenue 3) Satisfied citizens in government service delivery 4) Time reduction in obtaining government services 5) Reached top position in Ease of Doing Business Index | Output indicators 1) # of organizations linked 2) # of other clusters integrated to the "single window" 3) # / % of staff trained on Gov.lk ("Single Window") Outcome indicators 1) % of surveyed organizations satisfied with the software solutions provided. 2) Sri Lanka's Position in eGovernment Ease of Doing Business Index 3) % of increase in government revenue 4) % of time reduction in obtaining government services | Regular M&E assessment on Gov.lk "Single Window" development and usage by government offices and citizens. - Monthly Reporting Rapid assessment in achieving intended intermediate outcomes including Ease of Doing Business Index - Quarterly | M&E Unit in collaboration with independent M&E consultants | Kanchana Thudugala | The project was on hold after 2016 and reinitiated in 2019. During 2019, a consultant was hired to manage key components of middleware infrastructure. The contract period is from 24th Sep 2019 to March 2020.
7 | 25 | Ratification, Awareness, Promotion and Monitoring of e-Government Policy and Strategy and related activities | The project aims to make sure that the e-Government Policy and e-Government Strategy is ratified and adopted by the entire Government sector in Sri Lanka. | To promote effective implementation of eGovernment Policy and Strategy and making appropriate awareness | Completed activities as of 31 December 2019: In order to finalize the eGoverment Policy, two public consultation were conducted and obtained public opinions on eGovernment Policy. Further, the eGovernment policy was reviewed by Key Government CIOs and Senior Government Officials through series of Workshops. Currently, reviewed and finalized versions of eGovernment Policy is ready to submit for Cabinet Approval. Activities planned for 2020: 1) Awareness and Capacity building on eGovernment policy 2)Print eGov policy document and eGovernment policy launch 3) Public Hearing Workshops and Comprehensive workshop with private sector 4) Communication campaign for eGovernment policy 5)established effective M&E mechanism to ensure adoption of the eGov policy | 2016.May | 2018.Dec | 2019.Dec | 0 | 3.5 | 12% | 18% | 50% | 0% **No activities were initiated due to delay of approving procurement plan. | 0 | 0 | 0.8 | 1.2 |  | 90% | 100% |  | 1)Final draft of the Digital Government Policy document is ready to obtain Cabinet Approval 2) further public consultations to obtain public opinions on eGovernment Policy | 1) Improved adoption of the policy in key government organizations (Ministries, Departments, Selected statutory bodies, Provincial councils, District and divisional secretariats) are complying with key policy requirements | Output indicators 1)Final draft of the Digital Government Policy document is ready to obtain Cabinet Approval 2) further public consultations to obtain public opinions on eGovernment Policy Outcome indicators 1) Improved adoption of the policy - 50% of key government organizations (Ministries, Departments, Selected statutory bodies, Provincial councils, District and divisional secretariats) are complying with key policy requirements by end of 2020 | Regular M&E assessment on eGov Policy adoption by Government institutions.. - Monthly Reporting Rapid assessment in achieving intended intermediate outcomes - Quarterly | M&E Unit in collaboration with independent M&E consultants |  | NPD Approval is required for 2020
8 | 27 | Implementation of Cross Government Digital Document Management System | The project is to help the government to securely manage the ever-increasing paper documents. Upon completion, government organizations will be able to digitize and securely store all their documents via the proposed government digital document management system. Implementation of Digital document management systems applications provide facility to storage, software and licensing for organizations. This will enable all documents to be digitized and digitized copies stored in LGC 2.0 cloud storage. Further, relevant organisations will be able to search, retrieve and share any documents with the assurance that the security of the respective documents is ensured. | 1) To improve efficiency and effectiveness of the government organizations through implementing a secured, and reliable Cross Government Digital Document Management System | Completed activities as of 31 December 2019: Completed system study and UAT for 20 organizations (out of 20) and completed the system deployment. Activities planned for 2020: 1) Feasibility Study for selected 20 organisations 2) Configure the Digital Document Management System for selected organisations 3) Deploy necessary hardware resources to the selected government organizations 4) Train staff 5) Provide Maintenance and support 6) Regular monitoring and evaluation | 2016.Mar | 2018.Dec | 2019.Dec | 401 | 6.2 | 20% | 31% | 21% | 13% | 0 | 0 | 0 | 6.2 |  | 10% | 25% | 50% | 1) Established Cross government digital document management system in selected organizations 2) Integrated the system with related stakeholder organizations 3) Upgraded related systems infrastructure at the selected government organizations. 4) Trained staff in operating the Cross Government Digital Document Management System 5) Outcome Evaluation carried out to understand lessons learned in the previous phase | 1) Reduction in processing time to delivery of service. 2) Reduction of admin cost of the organization 3) Users satisfied with the service | Output indicators 1) # of Organizations Established CDDMS in selected 40 organizations (Target : 40 by end of 2020) 2) # of organizations which completed the Integration of the system. 3) # of organizations which completion the Upgrade of related systems infrastructure 4) # of trained staff in operating the Cross Government Digital Document Management System 5) % of completion of Outcome Evaluation carried out by end of 2020 - to understand lessons learned in the previous phase Outcome indicators 1) % of reduction in processing time to delivery of service (Target; At least 20% by December 2020) 2) % of annual reduction of admin cost of the organization (Target -At least 10% annual reduction) 3) % of surveyed users satisfied with the service (Target - At least 70% by December 2020) | % completion of the system - monthly reporting Regular M&E assessment on the adoption of the new system - quaterly reporting . - Rapid assessment in achieving intended intermediate outcomes - Quarterly Periodical surveys to assess final outcomes efficiency - Bi Annually | Collection of monthly ptogree related data- ICTA M&E team in colaboration with PM Indipendent quality checks and varifications by the external M&E firm Periodical outcome assessment as part of the bi annual e Gove evaluation assessment by an indipendent party | Gavashkar Subramanium | NPD Approval is required for 2020
9 | 30 | ICT Solution for Government Analyst's Department (GAD) | Government Analyst's Department (GAD) is engaged in very important functions to assist the government to ensure food safety and support law and order in the country. Although GAD works very closely with several other Government organizations, GAD still uses manual operations and basic some legacy systems. ICT can significantly increase the efficiency and effectiveness of the processes carried out by GAD. Both internal and external stakeholders of GAD and citizens will be benefited greatly by increasing the speed, efficiency and accuracy of GAD outputs by introducing proper ICT solutions. | 1) To make processes of GAD more efficient and effective by introducing ICT solutions and thereby make internal users, external stakeholders and citizens satisfied. 2) To use latest and related technologies which can optimize the functions of GAD. 3) To provide/improve facilities within the department. 4) To adhere with the standards used by similar organizations in the world. | Completed activities as of 31 December 2019: i. The project plan ii. SRS iii. Software architecture document iv. Test plans v. Test cases and test scenarios for 1st, 2nd & 3rd iterations vi. UAT Test cases Activities planned for 2020: 1) CR changes, UAT and OAT acceptance. 2) Arrange trainings for 50 internal users at GAD. | 2016.Mar | 2018.Dec | TBD | 40 | TBD | 31% | 19% | 21% | 0% ** The project was completed up to UAT stage in 2018, but, No activities were carried out during 2019 as UAT was not accepted by the GAD | 0 | 0 | 0 | 9 |  | 80% | 90% | 100% | 1) ICT solutions implemented and deployed. 2) Trained officials of GAD | 1) Time reduction in handling cases (eg: court orders) 2) Increased the # of cases handled and reports are produced per day 3) Staff satisfied with the ICT solution 4) Clients (government complains representative & end customer) satisfied with efficiency of the system | Output indicators 1) % of completion deployment of ICT solutions (Target- by Dec 2020) 2) # of officials trained of GAD (Target- 50 officials by Dec 2020) Outcome indicators 1) Time reduction in handling cases (eg: court orders) (Target - at least 10% annual time reduction by Dec 2020) 2) Increased the # of cases handled and reports are produced per day (Target - 20% annual increased) 3) % of Staff satisfied with the ICT solution (target-at least 70% surveyed staff satisfied by Dec 2020) 4) % of Clients (government complains representative & end customer) satisfied with efficiency of the system(Target - at least 70% surveyed clients satisfied by Dec 2020) | Regular M&E assessment on ICT Solution for GAD - Monthly Reporting Rapid assessment in achieving intended intermediate outcomes - Quarterly | M&E Unit in collaboration with independent M&E consultants | Indumini Kodikara | NPD Approval is required for 2020
10 | 35 | Implementation of Electronic Medical Records in Sri Lankan Government Hospitals (Digital Health Project) – Support and Maintenance | The purpose of this project is to provide support and maintenance services for 40 hospitals with the Hospital Health Information Management System (HHIMS) | 1. To increase the Electronic Medical Records coverage of the selected hospitals up to 80% from the total patients who access the health services. 2. To ensure availability of updated, accurate information for patient care and planning of health services. 3. To improve quality and efficiency in service delivery, governance, accountability and effective use of resources of the government hospitals. 4. To improve the capacity of health authorities to detect emerging and re-emerging diseases and take necessary preventive actions. 5. To insure the sustainability of HHIMS in the selected hospitals | 1. Conduct capacity building programmes for the health staff and handover the system to respective hospitals 2. Completion of implementing HHIMS in 5 hospitals 3. Support and maintenance of HHIMS in 40 hospitals 4. Organize official launching ceremonies of the selected hospitals | 2016 Mar | 2019 Dec | N/A | 1805.44 | 8.51 | 10% | 30% | 35% | 25% | 0.03525 | 0.1065 | 0.919 | 5.01 | 10% | 30% | 70% | 100% | 1. Established EHR systems (HHIMS) in 40 Government hospitals 2. Trained hospital staff members to manage the EHR systems effectively 3. Issued the Electronic patient cards 4. Provided personal electronic medical records for 80% of the patients who access the health services in the selected hospitals | 1) Reduction of waiting time of the patients to get the treatments 2) Patients satisfied with the quality of the services received 3) Increased the number of patients registered in the system | Output Indicators 1. No of EMR systems established in the Government Hospitals (Target - 40 Hospitals) 2. No of staff trained (Target - 50 staff) 3. No of electronic patient cards issued (Target - 1.5Mn by End of 2020) 4. No of electronic patient records available (Target - 3Mn records by end of 2020) Outcome indicators 1)15% annual reduction of waiting time of the patients to get the treatments 2) at least 70% of patients registered satisfied with the quality of the services received 3) # of patients registered in the system (target- 3,000,000 patients registered by December 2018) | Regular M&E assessment on Project - Monthly Reporting Rapid assessment in achieving intended intermediate outcomes - Quarterly Periodical outcome assessment - e Health Survey in campared to the e Health baseline survey | Collection of monthly ptogree related data- ICTA M&E team in colaboration with PM Indipendent quality checks and varifications by the external M&E firm Periodical outcome assessment as part of the bi annual e Gove evaluation assessment by an indipendent party | Shriyananda Rathnayake | This project was approved for three years from 2016 to implement EMR systems in 300 Govt hospitals. The target for the initial year was 45. The preparatory activities were completed in 2016 after obtaining the approval from NPD in March 2016 and Cabinet of Ministers in Sep. 2016. The project supported to implement EMR systems in 49 hospitals in 2017. However the budget of the project was transferred to Ministry of Health in 2018 on a decision of the Treasury.
11 | 36 | e-Heritage Project: Cutting-edge Technology for Heritage Information | This project will develop an e-heritage framework with mobile applications and web services which will provide location based information for tourists on their points of interest using innovative information and communication technologies. | 1) To improve tourists’ access to information, tourists’ knowledge and satisfaction on seeing heritage sites through comprehensive digital heritage framework to raise Sri Lanka’s image as a Heritage Destination | Completed activities as of 31 December 2019: 1. "Heritage Sri Lanka" Mobile and Web application development completed and become operational. (https://www.heritagesrilanka.gov.lk). Activities planned for 2020: 1) to appoint Review Committees (Assignment Basis) -Validation of Contents 2) to develop content for the data warehouse heritage framework and mobile applications in selected 100 sites (Text, Voice, Photo and VR) 3) to finalize Content framework and mobile application and content integration 4) to establish "Unique Identifier Codes" at sites 5) to conduct Mid-term Review 6) Conduct awareness and promotional campaign | 2017.Mar.0 | 2018.Dec | 2020.Dec | 102.1 | 11.62 | 3% | 44% | 34% | 17% | 0.0078 | 0 | 3.06 | 7.65 |  | 90% | 95% | 100% | 1) Completed eHeritage Sri Lanka mobile and web application 2) Heritage Sri Lanka mobile and web apps readily available for public 3) Completed of digital contents on archiological sites 4) Heritage Sites, Monuments, Buildings, Other Structures and cultural Events completed with digital content (Text, Photos, Audios) 5) Completed development of Sri Lanka Museums mobile application | 1) Users have facility to login and downloaded information from Heritage Site 2) Foreign tourist used heritage site to obtained information. 3) Students and researchers accessed for accurate information for academic purposes. 4) Users satisfied with the information provided heritage Sites | Output indicators 1) Completed eHeritage Sri Lanka mobile and web application by Dec 2019 2) # of downloads (Android app) Heritage Sri Lanka mobile and web apps readily available for public 3) Completed of digital contents on 100 sites by Dec 2020 4) Heritage Sites, Monuments, Buildings, Other Structures and cultural Events completed with digital content (Text, Photos, Audios) 5) Completed development of Sri Lanka Museums mobile application Outcome indicators 1) # of users login and downloaded information from Heritage Site (Target : 1000 users ) by December of 2020 2) % of Surveyed foreign tourist used heritage site to obtained information (Target - 20% by Dec 2020) 3) % of students and researchers accessed for accurate information for academic purposes (Target - 30% by Dec 2020) 4) % of surveyed users satisfied with the information provided heritage Sites- (50% of surveyed users) | Regular M&E assessment on eHeritage Project - Monthly Reporting Rapid assessment in achieving intended intermediate outcomes - Quarterly Periodical surveys to assess final outcomes - Annually | Collection of monthly ptogree related data- ICTA M&E team in colaboration with PM Indipendent quality checks and varifications by the external M&E firm Periodical outcome assessment as part of the bi annual e Gove evaluation assessment by an indipendent party | Shriyananda Rathnayake | 11.62 Mn, Budget Allocation provided in the 2020 action plan is disbursement target for the year. But the total budget requirement is 28.6Mn for procurement and operational for the whole project. However, the balance 16.98 Mn (28.6Mn - 11.62Mn) will spill over to 2021.
12 | 39 | National Spatial Data Infrastructure (NSDI) - Phase II | Development of a single platform for Spatial Data of the Government organizations, private and public sector. | 1)To enhance convenience and optimum use of up-to-date and reliable spatial data for making institutional and operational decision making process 2)To establish more effective, innovative and varied citizen services and applications across all sectors . | Completed activities as of 31 December 2019: Phase I of the NSDI Platform development was completed and now it is on live (www.nsdi.gov.lk) 25 Stakeholder organization has shared 125+ data layers with NSDI NSDI Policy is in draft stage - to be finalized and obtained cabinet approval Activities planned for 2020: 1. Functionality improvements of the NSDI System. 2. Development and integration of the Educational GIS Module to NSDI 3. Conduct Awareness and Change Management programmes (Multiple programmes) 4. Staff capacity building 5. Obtain support and maintenance services for the system 6. Obtain cabinet approval for the NSDI Policy and Establishment of the NSDI Secretariat. 7. Establishment of the NSDI Secretariat. * Acquire office location, equipment and furniture * Recruitment of Project Staff for NSDI Secretariat | 2016.Feb.25 | 2018.Dec | 2019.Dec | 530 | 52 | 27% | 31% | 29% | 9% | 0 | 1.5169 | 10.7 | 1.25 |  | 97% | 99% | 100% | 1) Phase I - Completed the NSDI Platform (www.nsdi.gov.lk) 2) Phase II - Developed other functionalities of NSDI 3) NSDI Policy is developed 4) NSDI Secretariats established | 1) Organizations accepted that their decision making process improved through usage of NSDI 2) Users satisfied with the NSDI system 3) Users accessed to sensitive data through payment gateways 4) Varied geo specific services and mobile apps available | Output indicators 1) % of completion of Phase I - Completed the NSDI Platform (www.nsdi.gov.lk) 2) % of completion of Phase II - Developed other functionalities of NSDI 3) % of completion of NSDI Policy 4) % of works completed of NSDI Secretariats established Outcome indicators 1) % of surveyed organizations accepted that their decision making process improved through usage of NSDI (Target - 30% accepted by Dec 2020 2) % of surveyed users satisfied with the NSDI system (Target - 50% satisfied by Dec 2020) 3) % of users accessed to sensitive data through payment gateways(Target- 40% of users by Dec 2020 4) # /type of varied geo specific services and mobile apps available (Target : 5 apps ) | Regular M&E assessment on NSDI Project- Monthly Reporting Rapid assessment in achieving intended intermediate outcomes - Quarterly Periodical surveys to assess final outcomes - Annually | Collection of monthly ptogree related data- ICTA M&E team in colaboration with PM Indipendent quality checks and varifications by the external M&E firm Periodical outcome assessment as part of the bi annual e Gove evaluation assessment by an indipendent party | Indumini Kodikara | NPD Approval is required for 2020
13 | 43 | Web development initiative | With the increasing demand for online services and the advancement of the technology it is essential to upgrade the existing web sites to provide more interactions with the citizens and to offer services online in a secure manner. Further, proper framework is needed to upgrade and develop government websites on a continuing basis. The framework should include a common set of standards for upgrading a web site and exposing online services to citizens. | 1) To develop a framework to upgrade the existing government websites, in a more interactive, effective and efficient manner. 2) To address the security and scalability requirements of existing government websites with the new framework; the framework will be developed to align with the government web standers published by ICTA. | Completed activities as of 31 December 2019 380 websites (331 for Divisional Secretariat Offices, 25 Districts Secretariat Offices and 24 other organizations) were developed and launched. Provided one year support and maintenance service through the vender during 2019. Planned activities for 2020: 1) Support and maintenance 2) Website migration | 2016.Apr.19 | 2018.Dec | 2019.Decr | 61.5 | 0.5 | 2% | 67% | 24% | 7% | 0.43192 | 0 | 0.068082 | 0 |  | 110% | 120% | 130% | 1) Developed 380 websites (331 for Divisional Secretariat Offices, 25 Districts Secretariat Offices and 24 other organizations) 2) Provided one year support and maintenance service through the vender during 2019 3) 357 organizations of website migrated to LGC 2.0 | 1) Citizens satisfied with the quality and reliable information available on the websites 2) Improved the efficiency of the service delivery of government organizations 3) Regulaly updated the websites with latest information | Output indicators: 1)# of websites Developed (Target - 331 for Divisional Secretariat Offices, 25 Districts Secretariat Offices and 24 other organizations) 2) Provided one year support and maintenance service through the vender during 2019 3) # of organizations of website migrated to LGC 2.0 (Target - 357 Websites) Outcome indicators: 1) % of surveyed citizens satisfied with the quality and reliable information available on the websites (Tartget - 40% by Dec 2020) 2) 50% improved the efficiency of the service delivery of government organizations 3) Websites are not updated with latest information (Yes/No) | Regular M&E assessment on effective usage of the ETFB system - Monthly Reporting Rapid assessment to measure intermediate outcomes - Quarterly | M&E Unit in collaboration with independent M&E consultants | Bhagya Kumarasinghe | NPD Approval is required for 2020
14 | 44 | Development of Electronic Services | ICTA supports govt organizations to automate key public services. to provide those service as eServices and mobile applications. ICTA is to continue maintaining the existing Lanka Gate infrastructure to ensure availability of its services and smooth operations. | 1) To provide citizen centric and business friendly public services. Through multiple delivery channels. Special mobile by using payments platforms. | Completed activities as of 31 December 2019 Development of twelve e-government services, Six eServices have been lunched and six eServices are yet to be launched. Planned activities for 2020: 1) Identify potential government organizations and eService for implementation. 2) Finalize and signoff requirements 3) Develop the systems with user acceptance 4) Release the solution | 2016.May | 2018.Dec | 2019 Dec | 120 | 7.5 | 28% | 53% | 13% | 2% | 0 | 6.9573 | 3.08 | 0 |  | 98% | 100% |  | 1) 12 Online Services developed and deployed 2) Finalize and signoff of 12 eServices developed 3) Support and maintenance activities | 1) Reduction of time taken to obtain services 2) Increase of users of e services | Output indicators: 1) # of Online Services developed and deployed (Target - 12 Online eServices) 2) # of Finalize and signoff of eServices developed (Target - 12 eServices) 3) Support and maintenance activities Outcome indicators: 1) % of annual reduction of time taken to obtain services (Target - at least 15% annual reduction of time) 2) % of annual increase of users of e services (Target - at least 10 % annual increase) | Regular M&E assessment on usage of the eServices - Monthly Reporting Rapid assessment to measure intermediate outcomes - Quarterly | M&E Unit in collaboration with independent M&E consultants | Kanchana Thudugala | NPD Approval is required for 2020
15 | 45 | Management and Operations of Government Information Centre (GIC) | Government Information Center (GIC) aims at providing government information in the most effective, efficient and user friendly manner (through 1919 call center). | 1) To provide information about Government services in the most effective, efficient and friendly manner. 2) To use ICT and technology including the social media effectively to provide government information. 3) To encourage the government sector to be more proactive in providing information effectively. 4) To increase the citizens’ engagement by offering convenient mechanisms to reach the government. | Completed activities as of 31 December 2019 Call Centre established and managing and operation of the call Centre is ongoing. Planned activities for 2020: 1) Setting up, Managing and Operation of Call Centre 2) GIC Sign Language Services for Deaf Persons 3) Revamping the GIC Portal and Development of the GIC Mobile Application 4) implementation of new approach for GIC operations and management to improve the citizen centric services as a public private partnership | 2016.Feb | 2018.Dec | 2019.Dec | 105.9 | 20.7 | 45% | 10% | 29% | 3% | 0 | 13.6748 | 6.86 | 9.2 | 90% | 95% | 100% |  | 1) Successfully Operate of the Call Centre and the knowledge base 2) Periodically update of knowledge base 3) Completed workshops on managing website, validate and update knowledge base etc. for approximately 200 government officers | 1) Citizens who accessed to GIC accept that they received accurate and reliable information | Output indicators 1) %/# of Successfully Operate of the Call Centre and the knowledge base 2) # of organizations periodically update of knowledge base 3) # of Completed workshops on managing website, validate and update knowledge base etc.(Target - approximately 200 government officers) Outcome indicators 1) % of surveyed citizens who accessed to GIC accept that they received accurate and reliable information (Target - at least 70% of surveyed citizens) | Regular M&E assessment of Government Information Centre Web Portal and Mobile Application -Monthly Reporting Rapid assessment to measure the intermediate outcomes - Quarterly | M&E Unit in collaboration with independent M&E consultants | Gavashkar Subramanium | NPD Approval is required for 2020
16 | 48 | ICT Human Resource Capacity Building for Government Digital Transformation | Overall goal of this initiative is to empower and build required capacities among public sector employees at all levels to enable effective delivery of citizen centric public services. | 1) To make Government leadership positive and competent towards driving ICT enabled public service excellence 2) To develop a pool of skilled senior government officials who could drive and facilitate the implementation of next phase of government 3)To empower CIOs across government by providing focused and continued capacity building opportunities. 4) To provide eGovernment related knowledge and skills to Government officials | Completed activities as of 31 December 2019 The eLearning platform for Government officials is completed and launched. Now it is in operations. 30 CIOs completed Master program on governance at PIM Planned activities for 2020: 1) Enhance Egov Learning Platform - Phase II 2) Essential Skills for eGov Change Management 3) Change Management Course for Government Officials 4) Continuous Change Management Activities for Key eGov Projects 5) Create Digital Government Transformation Video 6) Dedicated Media Programmes through Electronic Media for government digital transformation 7) Continuous Outreach and Awareness through Printed Media 8) Awareness Creation Initiatives through Social Media 9) Continuous Journalists Awareness Activities 10) Digital Transformation Approach and Road-map For Government 11) Strategic Interventions for Digital Adoption in Digital Government Transformation 12) CIO 2.0 Initiative 13) Continues Key Stakeholder Engagement Initiatives | 2016.Apr. | 2018.Dec | 2019.Dec | 382 | 29 | 31% | 26% | 25% | 8% | 0 | 0 | 8.06 | 19 |  | 92% | 95% | 100% | 1) e-Learning platform completed and operational 2) completed integration of Right to Information Act. In the eLearning platform. 3) CIO completed the master programme on Governance | 1) Government officers enrolled for online courses on eLearning Platform. 2) Courses available through the e Learning Platform | Output indicators 1) % of completion of e-Learning platform and operational 2) % of completion of integration of Right to Information Act. In the eLearning platform. 3) # of CIO completed the master programme on Governance Outcome indicators 1) # of government officers enrolled for online courses on eLearning Platform. 2) # of courses available through the e Learning Platform | Regular M&E assessment of usage of eLearning Platform and CIO engagement in eGoverment implementation - Monthly Reporting Rapid assessment to measure the intermediate outcomes - Quarterly | M&E Unit in collaboration with independent M&E consultants | Sameera Jayawardena | NPD Approval is required for 2020
17 | 51.1 | Citizen Empowerment and Connectivity Development including Wi-Fi Programme – Citizen Service Governance System (Enhancement ) | Provide a common Wi-Fi governance system with user registrations, single sign-on via public free Wi-Fi infrastructure throughout the country. | 1) To design, develop and implement a highly efficient, reliable, secure and scalable free Wi-Fi governance system. | Completed activities as of 31 December 2019 Implemented the Free Wi-Fi movement with the assistance of the Telecommunication Service Providers : SLT, Mobitel, Dialog, Lankacom, Lankabell and Etisalat Altogether, installed 800 boards Completed 1400+ free Wi-Fi hotspots jointly with Telcos and LGN 2.0 A user receives 100MB data per calendar month Common authentication platform established by integrating systems of Telcos and LGN. Planned activities for 2020: 1) Initiate discussions with key stakeholders 2) Conduct situation analysis on free Wi-Fi usage 3) Conduct promotional and awareness activities 4) Conduct Procurement activity 5) Monitor and evaluate the progress | 2017.May | 2018.Dec | 2019.Dec | 397 | 73.05 | 45% | 10% | 16% | 7% | 0 | 0 | 1.4 | 5.56 |  | 80% | 90% | 100% | 1) Further improved the Free Wi-Fi facility with the assistance of the Telecommunication Service Providers 2) Installed Wi-Fi boards 3) Completed free Wi-Fi hotspots 4) A user receives 100MB data per calendar month 5) Established common authentication platform | 1) Increased number of users and usage of free public Wi-Fi facility | Output indicators 1) Further improved the Free Wi-Fi facility with the assistance of the Telecommunication Service Providers 2) # of boards Installed (Target -800 boards) 3) # of Completion of free Wi-Fi hotspots (target - 1400+ hotspots) 4) A user receives 100MB data per calendar month 5) % of completion of Establishment of common authentication platform Outcome indicators 1) % of increased number of users and usage of free public Wi-Fi facility (Target - 30%) | Regular M&E assessment of Wi-Fi Programme - Monthly Reporting Rapid assessment to measure the intermediate outcomes - Quarterly | M&E Unit in collaboration with independent M&E consultants | Gavashkar Subramanium | NPD Approval is required for 2020
18 | 62 | Video Conferencing Facilities to the Ministries and Government Institutions | An inter ministry/department video conferencing infrastructure and solution to enable these organization to facilitate meetings via this facility. This initiative will enable attendees to connect to meeting and conferences from any location enabled with this facility. | 1) To improve the efficiency, speed-up decision making, reduce costs and save time of the Government officials to better service delivery by adapting Video Conferencing Solution within and between the Ministries and Government organizations. | 1) Conduct a feasibility study to identify technology and locations for piloting 2) Conduct a baseline Study 3) Conduct procurement activity 4) Deploy Video Conferencing facility 5) Conduct necessary training/awareness to the Officials 6) Monitoring and evaluation of the performance | 2016.Mar | 2018.Dec | 2020.Dec | 193 | 25 | 10% | 35% | 16% | 0% Two bidding processes were cancelled by PPCs after completion of Technical evaluations. The project was on hold due to budget constraints in 2019 | 0 | 0 | 0 | 0 |  | 25% | 60% | 100% | 1) Proof of concept for 3 organizations 2) Completed pilot implementation of video conferencing facilities 3)Trained intended users of the system (government officials) 4) Complete the feasibility study | 1) Annual cost reduction for traveling and meetings 2) Annual reduction in travel time for meetings 3) Improved decision making speed | Output indicators 1) Proof of concept for 3 organizations 2) Completed pilot implementation of video conferencing facilities in 30 organization by December 2020 3)100 intended users of the system (government officials) trained by December 2020 (Target - 100 government officers). 4) Complete the feasibility study Outcome indicators 1) % of annual cost reduction for traveling and meetings (Target - at least 20% of annual cost reduction) 2) % of annual reduction in travel time for meetings (Target - at least 20% annual reduction) 3) Improved decision making speed | Regular M&E assessment of Video Conferencing Project - Monthly Reporting Baseline Survey - 1st quarter of the project Rapid assessment to measure the intermediate outcomes - Quarterly Outcome evaluation - End of the year | Collection of monthly ptogree related data- ICTA M&E team in colaboration with PM Indipendent quality checks and varifications by the external M&E firm Periodical outcome assessment as part of the bi annual e Gove evaluation assessment by an indipendent party | Gavashkar Subramanium | 25 organisations (Total locations are 100) will be piloted the Video Conferencing Project and Evaluated at the end of the year. Based on the successes of the pilot project, Video Conferencing Facility will be replicated to other 75 locations.
19 | 63 | eParliament | ICTA supports Parliament to strengthen the parliamentary process through digital technologies. | To further strengthen timely provision of information/documentation in a user friendly manner to the members & the parliament, and improve the information management system of parliament through establishing Electronic Document Management System (EDMS). | Completed activities as of 31 December 2019 Iteration 1 of the Document Management System completed has been fully completed and completed 70% of Iteration 2. Planned activities for 2020 1) Development of e-gov solution for digitizing two key processes. 2) Awareness and Change Management 3) Ensure reliability & sustainability of EDMS | 2017.Mar | 2018.Dec | 2019.Dec | 185 | 42.1 |  | 33% | 33% | 1% | 0 | 0 | 20.3 | 21.1 |  | 80% | 90% | 100% | 1) Completed Electronic Document Management System (EDMS) 2) Staff trained on managing of EDMS System | 1) Staff satisfied with the EDMS 2) Time reduced in managing documentation 3) User satisfaction with historical data analysis with the EDMS 4) Usage of digital technologies and application within the parliament premises 5) Cost reduction for processing documents | Output indicators 1) % of completion of Electronic Document Management System (EDMS) (Target - 100% completed by December 2020 2) # of Staff trained on managing of EDMS System (Target - 70 officials) Outcome indicators 1) % of surveyed staff satisfied with the EDMS 2) % of time reduced in managing documentation 3) Level of user satisfaction with historical data analysis with the EDMS 4) Level of usage of digital technologies and application within the parliament premises 5) % of cost reduction for processing documents | Regular M&E assessment of EDMS system - Monthly Reporting Periodic Rapid Assessments of intermediate outcomes of the project - Quarterly | M&E Unit in collaboration with independent M&E consultants | Sameera Jayawardena | NPD Approval is required for 2020
20 | 64 | eCabinet Project | The proposed information system is to accommodate all the functions of existing systems within the cabinet office. The proposed system will further cater to document archiving and management. It shall be accessed only through the cabinet office intranet, providing information security. | To strengthen the e cabinet system / communication and effective dissemination among the other government organization through establishing a IT system (by replacing obsolete system) | Completed activities as of 31 December 2019 Overall, project concept and the scope has been agreed with project owner (Office of the Cabinet Ministers). MoU between the Office of the Cabinet Ministers and ICTA has been signed. Planned activities for 2020 1) Establish a project steering committee 3) Appoint a deliverables review committee/team 4) Identify/gather requirements 5) Conduct Procurement activities 6) Carry out project implementation 7) Monitor implementation progress 8) Train staff (Cabinet ministry +cabinet office) 9) Evaluate performance improvement | 2017.Mar | 2018.Dec | 2019.Dec | 92 | TBD |  | 15% | 20% | * No activities were carried out during 2019. | 0 | 0 | 0 | 0 |  | 20% | 50% | 100% | 1) Completed the Document Management System | 1) Reduced paper usage 2) Annual reduction of translation time, dissemination of information to other line ministries | Output indicators 1) Iteration 1 of the Document Management System has been fully completed and iteration 2 and 3 completed 90% and 30% respectively Outcome indicators 1) 30 % reduced paper usage by 2021 2) 10% of annual reduction of translation time, dissemination of information to other line ministries | Regular M&E assessment of eCabinet Project - Monthly Reporting Periodic Rapid Assessments of intermediate outcomes of the project - Quarterly | M&E Unit in collaboration with independent M&E consultants | Wimal Pathirathne | NPD Approval is required for 2020
21 | 75 | Digital Libraries for Knowledge Enhancement | Project aims to establish 26 Digital Libraries by 2019, one in each District across the country and a separate digital library for National Library.(the project activities will be implemented with close collaboration with the National Library and Documentation Services Board). these digital libraries will be equipped with modern up-to-date ICT equipment. These equipment will be connected by a network and will be provided with high-speed internet. Support eservices like scanning, printing and photocopying will enable user to store / take-home information as they wish. | 1) To establish 26 model digital libraries, one in each district. 2) To provide convenient and affordable access to, and promote effective usage of electronic information/e books and educational materials to citizens. | Completed activities as of 31 December 2019 • established five digital libraries (public libraries) under Phase I (2017) • completed 90% of activities in three libraries under Phase II (2018) Planned activities for 2020 1) carry out stakeholder awareness and sign MOU with relevant Municipal Councils 2) collect information from National and International information sources, store and organize in digital form 3) install and customize Koha Integrated Library Management System for Public Libraries 4) establish model Digital Libraries with ICT infrastructure , modern library furniture and local Area Network 5) conduct training programs for library staff 6) establish efficient Project Operation mechanism 7) develop proper guideline to acquire and dissimilate information. | 2017.Mar | 2018.Dec | 2019.Dec | 225 | 4.48 |  | 26% | 60% | 10% | 0.01515 | 0 | 0.48 | 3.61 |  | 98% | 100% |  | 1) Digital Libraries completed in phase (I) opened to public 2) Koha Integrated library management system installed and customized 3) Staff trained (Change Management sessions conducted) for all selected public libraries 4) Completed installation of hardware and accessories 5) Completed installation of Modern library furniture and accessories 6) Completed installation of Network infrastructure with LAN 7) Completed Online and offline media campaigns 8) New Digital libraries established and opened to public | 1) 30 % increased of new registered users by Dec 2020 2) 10% of Increased revenue by accurately tracking of new user registrations and books borrowings and fees for late book returns by 2020 3) 60% increased access to library System and download of eBooks and other materials by Dec 2020 | Output indicators 1) # of Digital Libraries completed in phase (I) opened to public (Target: 18 Libraries). 2) # of public libraries - Koha Integrated library management system installed and customized (target : 18 public libraries ) 3) # of staff trained (# of Change Management sessions conducted) for all selected public libraries (target tbd) 4) % completion of installation of hardware and accessories (target : 18 new public libraries) 5) % completion of installation of Modern library furniture and accessories (target: 18 new public libraries) 6) % completion of installation of Network infrastructure with LAN ( target: to be implemented at 18 public libraries) 7) % completion of Online and offline media campaigns 8) # of new Digital libraries established and opened to public (target: 18 new libries) Outcome indicators 1) 30 % increased of new registered users by Dec 2020 2) 10% of Increased revenue by accurately tracking of new user registrations and books borrowings and fees for late book returns by 2020 3) 60% increased access to library System and download of eBooks and other materials by Dec 2020 | Regular M&E assessment of Digital Library Project - Monthly Reporting Periodic Rapid Assessments of intermediate outcomes of the project - Quarterly | Collection of monthly ptogree related data- ICTA M&E team in colaboration with PM Indipendent quality checks and varifications by the external M&E firm Periodical outcome assessment as part of the bi annual e Gove evaluation assessment by an indipendent party | Shriyananda Rathnayake | NPD Approval is required for 2020.
22 | 76 | Smart Society and Citizen Capacity Building | This project will enable a social movement to foster ethical and responsible use of emerging ICT technologies for Citizen Empowerment. Further, this will provide strategic, technological and commercial foundation needed to encourage, and promote use of all social media and emerging Information & Communication Technologies and develop an environment conductive to the achievement of the nation’s intellectual, cultural and social aspirations through ICT. | 1) To facilitate transformation of the current society through effective usage of digital technologies 2) To improve competencies among all citizens to become active participants in the digitally empowered society | Completed activities as of 31 December 2019 860 of Smart Social Circles established. Planned activities for 2020 1) facilitate for establishing SSC's Island-wide 2) conduct SSC awareness creation activities 3) hire coordinators for implementing SSC 4) conduct National Launch and Citizen forum 5) develop of SMART citizen applications 6) conduct Suhuruliya women empowerment activities | 2017.Mar | 2018.Dec | 2019.Dec | 154 | 22 |  | 13% | 59% | 16% | 0.051684 | 0 | 7.5 | 15 |  | 95% | 100% |  | 1) Established DS level SMART Social Circles (SSC) 2) new activists engaged on effective use of emerging ICT technologies and social media. 3) Rural women empowered through suhuruliya initiatives. 4) Completed Outcome Assessment Study | 1) Activate SMART Social Circles 2) Created Industry and partnerships 3) Women entrepreneurs improved their businesses using social media (Facebook) | Output indicators 1) # of DS level SMART Social Circles (SSC) established by October 2020 (target - 40). 2) # of new activists engaged on effective use of emerging ICT technologies and social media.(target -4000) 3) # of rural women empowered through suhuruliya initiative by December 2020.(target 2000) 4) Completed Outcome Assessment Study Outcome indicators 1) % of SMART Social Circles are active (Target - 60%) 2) % Industry and partnerships createdc(Target - 30%) 3) % of surveyed women entrepreneurs improved their businesses using social media (Facebook) (Target - 30%) | Regular M&E assessment of Digital Library Project - Monthly Reporting Periodic Rapid Assessments of intermediate outcomes of the project - Quarterly | M&E Unit in collaboration with independent M&E consultants | Sameera Jayawardena | NPD Approval is required for 2020.
23 | 80 | Software Solution for Plantation Sector (Manage Census Data) (Ministry of Hill Country New Villages, Infrastructure and Community Development) | Development of an ICT solution which could store, update and analyze census data collected from the plantation communities | 1) To develop a comprehensive software system/ database to record and manage census data of the plantation sector. The system will be highly critical for the Ministry to take evidence based decision on the development of the estate sector | Completed activities as of 31 December 2019 System requirement Specification (SRS) has been finalized and development of system is in progress. Planned activities for 2020: 1) Initiate the development 2) support and maintenance 3) Conduct training sessions for users | 2017.Mar | 2018.Dec | 2019.Dec | 1.7 | 1.8 |  | 19% | 37% | 9% | 0 | 0 | 0 | 0 |  | 75% | 85% | 100% | 1) Developed software solution for managing census data in the Plantation Sector 2) # of intended users trained | 1) level of satisfaction of quality of the data 2) level of data usage for decision making on the development of the estate sector | Output indicators 1) % of completion of software solution for managing census data in the Plantation Sector (Target - TBD) 2) # of intended users trained (Target -TBD) Outcome indicators 1) % of satisfaction of quality of the data (Target - TBD) 2) % of data usage for decision making on the development of the estate sector (Target - TBD) | Regular M&E assessment of Software Solution - Monthly Reporting Periodic Rapid Assessments of intermediate outcomes of the project - Quarterly | M&E Unit in collaboration with independent M&E consultants | Jagath Seneviratne | NPD Approval is required for 2020
24 | 82 | e-Swabhimani Annual Programme and Associated Activities | The project is to recognize creativity and the skills of local digital application developers that have a strong impact on the society and thereby provide a platform for them to showcase their products nationally and internationally. | 1) To promote and popularize the development of digital content and application that has a social impact. 2) To recognize and incentivize the best application developers and introduce them to the global market. | Completed activities as of 31 December 2019 Successful completed the e-Swabhimani event in 2019 Planned activities for 2020: 1) Awareness creation through a contracted Service Provider and calling for applications 2) Conducting the Grand Jury 3) Organizing Gala Awards Event 4) Capacity building of the winners & Nominate selected applications to regional and other international awards. |  | 2019.Jun | 2019.Dec | 30 | 10 |  | 100% | 100% | 100% | 0 | 0.22292 | 3.5 | 6.5 | 10% | 25% | 76% | 100% | Completed the eSwabhimani annual event successfully | 1) eSwabhimani winners are active and continue with improvement (Quantitative and Qualitative) 2) eSwabhimani winners believe that the recognition received from eSwarbimani helped to improve businesses and get into the international market (Qualitative and quantitative) | Outcome indicators 1) at least 70% of surveyed eSwabhimani winners are active and continue with improvement (Quantitative and Qualitative) 2) at least 70% of the Surveyed eSwabhimani winners believe that the recognition received from eSwarbimani helped to improve businesses and get into the international market (Qualitative and quantitative) | Regular M&E assessment of eSwabhimani Annual Programme - Monthly Reporting | M&E Unit in collaboration with independent M&E consultants | Indumini Kodikara | This is an annual project and achievement for each year (2017,2018 and 2019) is 100% NPD Approval is required for 2020
25 | 83 | Results Based Management : Monitoring and Evaluation | The aim of M&E is to measure the progress of achieving expected development results (outputs and outcomes) in independent and unbiased manner. M&E systems will be implemented across all the projects and programmes and need to be designed from the beginning of the project planning. M&E has a significant roll in planning the project based on Results Based Management Principles. For each project, detailed Log frames (LFAs) will be developed in consultation with primary stakeholders to define and develop shared knowledge on project objectives, impact, outcomes and outputs and data collection methods and responsibilities. | 1) To measure performance and results 2) To evaluate progress towards outcomes, 3) To promote institutional learning/ create knowledge based and learning culture 4) To improve focus on results and performance orientation and sustainability 5) To understand and negotiating stakeholder perspectives to promote ownership 6) To improve accountability for development results and sustainability | Completed activities as of 31 December 2019 ICTA completed the following surveys with the support of ICTA M&E Team completed following reports and activities; - Study on the effectiveness of CIO programme - Analysis of Feedback of LGN 2.0 awareness workshop in Colombo, Kurunagala, Galle Districts - Quarterly and monthly progress reports - Rapid Assessment of eRL System - Evaluation of the performance of Government Information Center - Rapid Assessment - e-Registration of Companies (ROC) Project - Outcome Assessment of Smart Social Circle project - Rapid Assessment of EPF System - Rapid Assessment of IWM System Monthly Report - 2B Report, Monthly Progress Report Quarterly Report - DPMM Report, Quarterly Parliamentarian Report Activities planned for 2020 1) to designing overall result frame work and M&E plan 2) to manage the M&E Consultant firm for ongoing data collection and conducting field monitoring visits 4) to conduct eGovernment Survey 6) Conducting Mid term evaluation -workshop- review progress with stakeholders identifying lessons learned, reallocating budgets 7) to carry out regular field visit to LGN and other key projects sites and produce brief M&E reports with forward looking recommendation 9) to prepare Annual Evaluation Report based on the evaluation activities carried out though out the year and submit to ICTA Board. | 2017.Mar | 2018.Dec | 2019. Dec | 348 | 20.5 |  | 30% | 40% | 30% All activates planned up to end of 2018 completed. M&E activities for the implementing projects are on going as basis as a routing function. | 0 | 0 | 5 | 9.5 | 10% | 40% | 70% | 100% | 1) (Monthly/quarterly/annual) reports submitted- (Quarterly reports - Department of Project Management and Monitoring, Parliament, Presidential Secretariats- Monthly report to ICTA Board and Line Ministry) 2. Completion of overall ICTA results framework and M&E Plan 3.External M&E firm hired and quarterly outcome assessment reports produced / submitted to ICTA management with corrective actions 4. Completion of e Government Survey 5. Completed Mid-Term Progress Review Workshop 6. Overall project evaluation including lessonslearned report completed | 1) Improved results of digitization projects implemented by ICTA 2) Timely and evidence informed decisions to improve program performances and results/outcomes 3)improved knowledge of stakeholder on the progress and outcome of the projects 4) Create a learning organization - learning based on the evaluations , improved knowledge of the results and take timely forward looking corrective actions | Output indicators 1) Submitted (Monthly/quarterly/annual) reports- (Quarterly reports - Department of Project Management and Monitoring, Parliament, Presidential Secretariats- Monthly report to ICTA Board and Line Ministry) 2. Completion of overall ICTA results framework and M&E Plan 3.External M&E firm hired and quarterly outcome assessment reports produced / submitted to ICTA management with corrective actions 4. Completion of e Government Survey by December 2020 5. Completed Mid-Term Progress Review Workshop (Yes/No) 6. Overall project evaluation including lessonslearned report completed by end 2020 Outcome indicators 1) Improved results of digitization projects implemented by ICTA 2) Timely and evidence informed decisions to improve program performances and results/outcomes 3)improved knowledge of stakeholder on the progress and outcome of the projects 4) Create a learning organization - learning based on the evaluations , improved knowledge of the results and take timely forward looking corrective actions | M&E has been recognized as a essential and rurine function to assess the outcome of the ICTA projects. The success of M&E is measured through adoption of M&E practices in the projects as well as number of reports produced on the progress of results achieved. | Internal M&E unit headed by Head of M&E is responsible for the entire M&E process ensure the consistance and indipendent nature external M&E firm is engaged in collection of outcome related data from the beneficiaries | Jagath Seneviratne | NPD Approval is required for 2020
26 | 84 | LGN 2.0 Enhancement- Phase 1 ( LGN 2.0 Training & Change Management and Awareness LGII Ticketing System & Enhancement) | Enabling the smooth operation of the Lanka Government Network & promote outcomes | 1) To ensure providing better awareness and knowledge for government officers and IT administrators 2) To ensure smooth migrations and transitions from LGN version 1.0 to version 2.0. 3) To maintain and support the LGN and LGC through LGII (Lanka Govt Information Infrastructure)( to avoid unnecessary overheads to ICTA) 4) To upgrade the capacity of LGII to ensure effective support for both LGC 1.0 and 2.0. 5) To establish LGN ticketing system for handling issues. | Completed activities as of 31 December 2019 1. Ticketing System for LGN Helpdesk implementation is completed. Testing is ongoing. 2. 100% completed the uplink cable installation (159 existing network connected to the LGN 2.0) Activities planned for 2020 1) Procurement activities for contract extensions and setting up new contracts for on-going services such as co-location and connectivity. 2) Procurement activities for critical upgrades (Ex: storage). 3) Regular maintenance work. 4) Procurement activities for selecting service providers for application migrations. 5) Migration and transition planning. 6) Train 860 IT administrators | 2017.Mar | 2018.Dec | 2020.Dec | 150 | 60.8 |  | 50% | 21% | 8% | 28.3477 | 5.2669 | 3.8502 | 3.1747 | 84% | 90% | 95% | 100% | 1) Completed and operational the Ticketing System for resolving of operational issues of LGN 2.0 2) IT admin officers trained 3) Completed the uplink cable installation | 1)Satisfied users about the LGN 2.0 2) Improved the utilization of LGN 2.0 network and facilities of intended government offices effectively utilizing LGN 2.0 network and facilities | Output indicators 1) Completed and operational the Ticketing System for resolving of operational issues of LGN 2.0 by December 2020 Target : 100% 2) IT admin officers trained by December 2020 (Target : 860 Officers in 35 Workshops (5 Days)) 3) 100% completed the uplink cable installation (159 existing network connected to the LGN 2.0) Outcome indicators 1)at least 70% of LGN 2.0 users (staff) satisfied about the LGN 2.0 2) Improved the utilization of LGN 2.0 network and facilities by Dec 2020- at least 70% of intended government offices effectively utilizing LGN 2.0 network and facilities by Dec 2020 | Regular M&E assessment of Software Solution - Monthly Reporting Periodic Rapid Assessments of intermediate outcomes of the project - Quarterly | M&E Unit in collaboration with independent M&E consultants | Ravindra Pathirana
27 | 85 | Industry Development Program | The Industry Development program (IDP) of ICTA has its primary role of being a catalyst of change in ensuring the future readiness of the technology ecosystem. The program has acted with foresight and have designed projects localized to Sri Lanka to align tech ecosystem with global trends. Overall objectives are to improve competitiveness in IT-BPM industry while creating IT-BPM related jobs across all sectors. IDP aims to improve export growth through innovation and entrepreneurship, improve supply of skilled professionals to satisfy growing IT-BPM market growth, establish a strong start up ecosystem in Sri Lanka and to create awareness and Positioning Sri Lanka IT/BPM sector globally. | Overall objectives: 1)To improve competitiveness in IT-BPM industry 2)To create IT-BPM related jobs across all sectors Specific Objectives: 1) To improve export growth through innovation and entrepreneurship. 2) To improve supply of skilled professionals to satisfy growing IT-BPM market growth. 3) To establish strong start up ecosystem in Sri Lanka. 4) To create awareness and Positioning Sri Lanka IT/BPM sector globally. | 1) Carry out Digital Business clinics for tech SME’s in Regions 2) Facilitate Digital Transformation of SME's in Regions 3) Implementation of Spiralation Program for tech start-ups 4) Implement Creative Education Initiatives (Teachers) 5) Implement Entrepreneurship awareness programs 6) Implement Startup Ecosystem Building Initiatives 7) Support to improve Market Access for Technology companies | 2017.May | 2018.Dec | 2019.Dec | 415 | 65 |  | 52% | 25% | 23% | 0.018298 | 4.8488 | 1.8426 | 52.9 | 25% | 50% | 75% | 100% | 1 ) Supported to Tech companies (under Digital Business clinics) 2) Trained the Youth on Entrepreneurs 3) Trained the teachers on creative education 4) Completed the Workforce survey | 1) Youth entrepreneurs have improved their business 2) Activated to Supported Start-ups 3) Created IT/BPM related rnew job opportunities by Dec 2020 4) Companies have improved International and Local Market access by Dec 2020 | Output indicators 1 ) Tech companies supported (under Digital Business clinics) by Dec 2020 (Target : 10) 2) Youth on Entrepreneurs trained by Dec 2020 ( Target # tbd) 3) Teacher trained on creative education by Dec 2020 (Target : 200) 4) Workforce survey completed by June 2019 Outcome indicators 1) Youth entrepreneurs have improved their business by Dec 2020 2) Supported Start-ups have active by Dec 2020 3) Created IT/BPM related rnew job opportunities by Dec 2020 4) Companies have improved International and Local Market access by Dec 2020 | Regular M&E assessment of Industry Development Programme- Monthly Reporting Periodic Rapid Assessments of intermediate outcomes of the project - Quarterly Periodical surveys to assess final outcomes - Annually | M&E Unit in collaboration with independent M&E consultants | Sachindra Samararatne | Even though the breakdown of physical progress given in annual basis since 2017, project activities have been planned in annual basis and achievement in each year is 100% NPD Approval is required for 2020
28 | 86 | Lanka Government Cloud 2.0, Phase 02 ( Centralized Gov email solution) | Enhance communication across the government through establishing centralized email solution. | 1) To enhance cloud environment including cross government email solution, government work flow system. | 1) Implementation of e-mails and collaborative tools 2) Implement 2nd zone for LGC 2.0 3) Finalize the implementation approaches for each item and specifications. 4) Conduct brainstorming, ratifications and consultation sessions. 5) Carry out respective procurement activities. 6) Implementation of work plan. 7) Carry out Testing, verification and acceptance processes. 8) Conduct awareness programs to government organizations and formulation of business models. 9) Implementing regular monitoring and periodical evaluations. | 2017.Mar | 2018.Dec | 2020.Dec | 2449.5 | 5.6 | _ | 22% | 1% | ** No activities were carried out during 2019. Physical progress shows very low as there were issues in obtain approvals. | 0 | 0 | 253 | 85 | 33% | 40% | 60% | 77% | 1) Conducted an audit on cloud standards and security compliance 2) Completed installation of the Cloud infrastructure (LGC 2.0) 3) Established government email solution 4) Email accounts (gov.lk) created for government staff | 1) Government staff used government email facilities 2) Government staff satisfied with the government email solution | Output indicators 1) Conducted an audit on cloud standards and security compliance 2) Completed installation of the Cloud infrastructure (LGC 2.0) by Dec 2020 Target : 100% completed 3) Established government email solution by Dec 2020 4) Email accounts (gov.lk)created for government staff by Dec 2020 Outcome indicators 1) at least 50 % of government staff used government email facilities by Dec 2021 2)at least 60 % of surveyed government staff satisfied with the government email solution | Regular M&E assessment of LGN 2.0 Phase 02 - Monthly Reporting Periodic Rapid Assessments of intermediate outcomes of the project - Quarterly | M&E Unit in collaboration with independent M&E consultants | Ravindra Pathirana
[10 empty] | 2611.66 |  |  |  |  | Q1: 106.5922; Q2: 217.4531; Q3: 1736.5133; Q4: 746.7963
Note : • Until end of 2019, the project progress percentages qare worked out based on physical progress measured against project designing and planning, Procurement process, and implementation progress and achievement of output. However, measuring outputs (physical progress) doesn’t reflect and sufficient to ensure achievement of project objectives and sustainability. • Therefore, in 2020 ICTA focused on promoting outcomes and sustainability related factors of the projects which completed more than 75% of output achievements. • In that case although the project is completed 100% in terms of achieving outputs still some more work has to be done until the outcome and sustainability is assured. • Example : LGN project has achieved its 100% physical progress by end of 2019 , but, usage and adoption shows very low based on the available M&E findings . During 2020, the project management teams is focusing more on adoption of the services provided under LGN.

## 2020 Procurement Plan
PROCUREMENT PLAN FOR THE YEAR 2020
Serial No | Procuring Entity (Department/Line Agency/Ministry etc) | Description |  |  |  |  | Procuring Category (Goods, Services, Works, Information Systems, Consultancy Services etc.) | Estimated Cost (Rs. Mn) | Source of Financing/Name of the Donor | Procurement method (ICB,LIB,LNB,NCB, National Shopping etc.) | Level of Authority (CAPC, SCAPC, MPC, DPC etc.) | Priority status U=Urgent P=Priority N=Normal | Current status of procurement preparedness activities | Scheduled date of commencement | Scheduled date of completion | Reference to Action Plan | Remarks | (Rs. Mn) (for Ministry Information Only) | 2019 New Procuremnt (Rs. Mn) | Saved | MDIIT Funding Available?
|  | NPD Approved Project No | (NPD Approved Project Name) | planned activties as per Actipon plan | Procurement Activity No. | Title of the Procurement activity
Saved
1 | ICTA | 1 | Lanka Government Network 2.0 | 1) Finalize the operational model of the LGN 2.0 after ending the contract period (from Oct-20 onwards)
2)Connecting Adjacent building of existing LGN sites
3) Provide LGN connectivity to new organizations
4) Carryout ongoing M&E activities
5) Conduct indipendent Outcome Evaluation
6) Prepare Project Completion Report
7) Improve adoption among intended users
8) Dismantle of LGN 1.0
|  | 3 | Lanka Government Cloud (LGC) 2.0 - Phase 1 (LGC2.0 Phase 1 Maintenance +LGC 1.0 maintenance) | 1) Provide Bare-Metal Server Facilities for General Cluster of Lanka Government Cloud 2.0
2) Provide Bare-Metal Server Facilities for Big-Data Cluster of Lanka Government Cloud 2.0
3) Provide for Co-location Services for Lanka Government Cloud 2.0
4) Installation, Configuration and Maintenance of Application Stacks for the Lanka Government Cloud 2.0
5) Mesosphere (Datacenter Operating System) Software License Subscriptions
6) Extension of the contract for LGC 2.0 and LGN 1.0 VPN links
7) Migrate all applications hosted in LGC 1.0 to LGC 2.0
8) LGC 1.0 Switch off and Dismantle
|  | 12 | Employee Trust Fund Management (ETF) System | 1. Hardware Devices and Supporting Software tools
|  | 13 | Integrated Welfare management System (IWMS) | 1) Complete the knowledge transfer
2) Enhancement of IWMS System - ( CR)
3) Conduct UAT Signoff
|  | 14 | eLocal Government Programme | Completion of eLG - LPOPP integration
|  | 22 | Implementation of Gov.lk “Single Window” for Cross Government (Cluster implementation) | 1) Continue managing the middlware infrastructure and common services
2) Transfer the responsibility of maintaining the online license issuance service to the ICTA technology team.
3) Technology upgrade and transfer the online services to the Lanka Government cloud 2.0
4) Ongoing discussions to implment the Import and Export Control backend application
|  | 25 | The project aims to make sure that the e-Government Policy and e-Government Strategy is ratified and adopted by the entire Government sector in Sri Lanka. | 1) Awareness and Capacity building on eGovernment policy
2)Print eGov policy document and eGovernment policy launch
3) Public Hearing Workshops and Comprehensive workshop with private sector
4) Communication campaign for eGovernment policy
5)established effective M&E mechanism to ensure adoption of the eGov policy
|  | 27 | Implementation of Cross Government Digital Document Management System | 1) Feasibility Study for selected 20 organisations
2) Configure the Digital Document Management System for selected organisations
3) Deploy necessary hardware resources to the selected government organizations
4) Train staff
5) Provide Maintenance and support
6) Regular monitoring and evaluation
|  | 30 | ICT Solution for Government Analyst's Department (GAD) | 1) CR changes, UAT and OAT acceptance.
2) Arrange trainings for 50 internal users at GAD.
|  | 35 | Implementation of Electronic Medical Records in Sri Lankan Government Hospitals (Digital Health Project) – Support and Maintenance | 1. Conduct capacity building programmes for the health staff and handover the system to respective hospitals
2. Completion of implementing HHIMS in 5 hospitals
3. Support and maintenance of HHIMS in 40 hospitals
4. Organize official launching ceremonies of the selected hospitals
|  | 36 | e-Heritage Project: Cutting-edge Technology for Heritage Information | 1) to appoint Review Committees (Assignment Basis) -Validation of Contents
2) to develop content for the data warehouse
heritage framework and mobile applications in selected 100 sites (Text, Voice, Photo and VR)
3) to finalize Content framework and mobile application and content integration
4) to establish "Unique Identifier Codes" at sites
5) to conduct Mid-term Review
6) Conduct awareness and promotional campaign
|  | 39 | National Spatial Data Infrastructure (NSDI) - Phase II | 1. Functionality improvements of the NSDI System.
2. Development and integration of the Educational GIS Module to NSDI
3. Conduct Awareness and Change Management programmes (Multiple programmes)
4. Staff capacity building
5. Obtain support and maintenance services for the system
6. Obtain cabinet approval for the NSDI Policy and Establishment of the NSDI Secretariat.
7. Establishment of the NSDI Secretariat.
* Acquire office location, equipment and furniture
* Recruitment of Project Staff for NSDI Secretariat
|  | 43 | Web development initiative | 1) Support and maintenance
2) Website migration
|  | 44 | Development of Electronic Services | 1) Identify potential government organizations and eService for implementation.
2) Finalize and signoff requirements
3) Develop the systems with user acceptance
4) Release the solution
|  | 45 | Management and Operations of Government Information Centre (GIC) | 1) Setting up, Managing and Operation of Call Centre
2) GIC Sign Language Services for Deaf Persons
3) Revamping the GIC Portal and Development of the GIC Mobile Application
4) implementation of new approach for GIC operations and management to improve the citizen centric services as a public private partnership
|  | 48 | ICT Human Resource Capacity Building for Government Digital Transformation | Planned activities for 2020:
1) Enhance Egov Learning Platform - Phase II
2) Essential Skills for eGov Change Management
3) Change Management Course for Senior Government Officials
4) Continuous Change Management Activities for Key eGov Projects
5) Create Digital Government Transformation Video
6) Dedicated Media Programmes through Electronic Media for government digital transformation
7) Continuous Outreach and Awareness through Printed Media
8) Awareness Creation Initiatives through Social Media
9) Continuous Journalists Awareness Activities
10) Digital Transformation Approach and Road-map For Government
11) Strategic Interventions for Digital Adoption in Digital Government Transformation
12) CIO 2.0 Initiative
13) Continues Key Stakeholder Engagement Initiatives
|  | 51.1 | Citizen Empowerment and Connectivity Development including Wi-Fi Programme – Citizen Service Governance System (Enhancement ) | 1) Initiate discussions with key stakeholders
2) Conduct situation analysis on free Wi-Fi usage
3) Conduct promotional and awareness activities
4) Conduct Procurement activity
5) Monitor and evaluate the progress
|  | 62 | Video Conferencing Facilities to the Ministries and Government Institutions | 1) Conduct a feasibility study to identify technology and locations for piloting
2) Conduct a baseline Study
3) Conduct procurement activity
4) Deploy Video Conferencing facility
5) Conduct necessary training/awareness to the Officials
6) Monitoring and evaluation of the performance
|  | 63 | eParliament | 1) Development of e-gov solution for digitizing two key processes.
2) Awareness and Change Management
3) Ensure reliability & sustainability of EDMS
|  | 64 | eCabinet Project | 1) Establish a project steering committee
3) Appoint a deliverables review committee/team
4) Identify/gather requirements
5) Conduct Procurement activities
6) Carry out project implementation
7) Monitor implementation progress
8) Train staff (Cabinet ministry +cabinet office)
9) Evaluate performance improvemen
|  | 75 | Digital Libraries for Knowledge Enhancement | 1) carry out stakeholder awareness and sign MOU with relevant Municipal Councils
2) collect information from National and International information sources, store and organize in digital form
3) install and customize Koha Integrated Library Management System for Public Libraries
4) establish model Digital Libraries with ICT infrastructure , modern library furniture and local Area Network
5) conduct training programs for library staff
6) establish efficient Project Operation mechanism
7) develop proper guideline to acquire and dissimilate information.
|  | 76 | Smart Society and Citizen Capacity Building | 1) facilitate for establishing SSC's Island-wide
2) conduct SSC awareness creation activities
3) hire coordinators for implementing SSC
4) conduct National Launch and Citizen forum
5) develop of SMART citizen applications
6) conduct Suhuruliya women empowerment activities
|  | 80 | Software Solution for Plantation Sector (Manage Census Data) (Ministry of Hill Country New Villages, Infrastructure and Community Development) | 1) Initiate the development
2) support and maintenance
3) Conduct training sessions for users
|  | 82 | e-Swabhimani Annual Programme and Associated Activities | 1) Awareness creation through a contracted Service Provider and calling for applications
2) Conducting the Grand Jury
3) Organizing Gala Awards Event
4) Capacity building of the winners & Nominate selected applications to regional and other international awards.
|  | 83 | Results Based Management : Monitoring and Evaluation | 1) to designing overall result frame work and M&E plan
2) to manage the M&E Fconsultant firm for ongoing data collection and conducting field monitoring visits
4) to conduct eGovernment Survey
6) Conducting Mid term evaluation -workshop- review progress with stakeholders identifying lessons learned, reallocating budgets
7) to carry out regular field visit to LGN and other key projects sites and produce brief M&E reports with forward looking recommandation
9) to preapre Anuual Evaluation Report based on the evaluation activities carried out though out the year and submit to ICTA Board.
|  | 84 | LGN 2.0 Enhancement- Phase 1 ( LGN 2.0 Training & Change Management and Awareness LGII Ticketing System & Enhancement) | 1) Procurement activities for contract extensions and setting up new contracts for on-going services such as co-location and connectivity.
2) Procurement activities for critical upgrades (Ex: storage).
3) Regular maintenance work.
4) Procurement activities for selecting service providers for application migrations.
5) Migration and transition planning.
6) Train 860 IT administrators
|  | 85 | Industry Development Program | 1) Carry out Digital Business clinics for tech SME’s in Regions
2) Facilitate Digital Transformation of SME's in Regions
3) Implementation of Spiralation Program for tech start-ups
4) Implement Creative Education Initiatives (Teachers)
5) Implement Entrepreneurship awareness programs
6) Implement Startup Ecosystem Building Initiatives
7) Support to improve Market Access for Technology companies
|  | 86 | Lanka Government Cloud 2.0, Phase 02 | ) Implementation of e-mails and collaborative tools
2) Implement 2nd zone for LGC 2.0
3) Finalize the implementation approaches for each item and specifications.
4) Conduct brainstorming, ratifications and consultation sessions.
5) Carry out respective procurement activities.
6) Implementation of work plan.
7) Carry out Testing, verification and acceptance processes.
8) Conduct awareness programs to government organizations and formulation of business models.
9) Implementing regular monitoring and periodical evaluations.

## Plan 2018 (hidden)
2018 Disbursement Plan (ver 2.5- 2018.06.19)
# | NPD Project # | Project Name | Project Duration (Years) | NPD Approved Year | Total Approved Budget (Rs. Mn) | 2018 Planned Budget | Allocation Code | Jan - Apr Invoices (Rs Mn)
ICTA Component | [8 empty] | Q1 | Q2 | Q3 | Q4
1 | 1 | Lanka Government Network (LGN) 2.0 | 3 | 2016 | 5124.88 | 507.58 | ICTA |  | 0 | 0 | 128.42 | 379.16
2 | 3 | Lanka Government Cloud (LGC) 2.0 | 3 | 2016 | 621.7 | 250.92 | ICTA |  | 0 | 85.15 | 96.96 | 68.81
3 | 12 | Employee Trust Fund Management (ETF) System | 3 | 2016 | 100 | 17.73 | ICTA |  | 0 | 2.46 | 3.27 | 12
4 | 13 | Integrated Welfare Management System | 3 | 2016 | 164 | 18 | ICTA |  | 0 | 0 | 17.75 | 0.25
5 | 30 | ICT Solution for Government Analyst's Department (GAD) | 2 | 2016 | 40 | 20.95 | ICTA |  | 0 | 0 | 10.21 | 10.74
6 | 39 | National Spatial Data Infrastructure (NSDI) | 3 | 2016 | 530 | 90.44 | ICTA |  | 0 | 13.95 | 17.1 | 59.39
7 | 44 | Development of Electronic Services | 2 | 2016 | 120 | 24.36 | ICTA |  | 0 | 0.02 | 8.85 | 15.49
8 | 51.1 | Citizen Empowerment and Connectivity Development including Wi-Fi Programme – Citizen Service Governance System | 3 | 2016 | 397 | 34.82 | ICTA |  | 0 | 1.5 | 14.15 | 19.17
9 | 80 | Software Solution for Plantation Sector (Manage Census Data) Ministry of Hill Country New Villages, Infrastructure and Community Development | 1 | 2017 | 1.7 | 2 | ICTA |  | 0 | 0 | 1.7 | 0.3
10 | 83 | Results based M&E , Implementation of ICTA Business Plan and key M&E activities | 3 | 2017 | 348 | 17 | ICTA |  | 0 | 7.6 | 5 | 4.4
11 | 85 | Industry Development Program | 1 | 2017 | 415 | 50 | ICTA |  | 0 | 8.3 | 22.19 | 19.51
12 | 63 | eParliament ( SW + Network) | 2 | 2017 | 185 | 77.52 | ICTA |  | 0 | 0 | 15.72 | 61.8
13 | 64 | eCabinet Phase 1 | 1 | 2017 | 92 | 7 | ICTA |  | 0 | 0 | 0 | 7
14 | 84 | LGN 2.0 Enhancement ( LGN IT Admin Training, LGN Ticketing System,) | 1 | 2017 | 150 | 98.8 | ICTA |  | 0 | 0 | 13.7 | 85.1
15 | 45 | Management and operation of Government Information Center (GIC) (HelpDesk + Website) | 3 | 2016 | 105.9 | 31.7 | ICTA |  | 0 | 14.4 | 7.2 | 10.1
16 | 48 | ICT Human Resource Capacity Building for Government (CIO training) | 3 | 2016 | 382 | 32.48 | ICTA |  | 0 | 0 | 8.05 | 24.43
17 | 86 | Lanka Government Cloud 2.0, Phase 02 ( Including LGN email solution) | 3 | 2017 | 2449.5 | 50.25 | ICTA |  | 0 | 0 | 4.7 | 45.55
18 | 27 | Implementation of Cross Government Digital Document Management System | 3 | 2016 | 401 | 6.25 | ICTA |  | 0 | 0 | 6.25 | 0
19 | 20 | Lanka Gate Infrastructure Maintenance /Related Services and Related Components (Eservices Maintenance) | 2 | 2016 | 61.41 | 6 | ICTA |  | 0 | 0 | 1.5 | 4.5
20 | 62 | Video Conferencing Facilities to the Ministries and Government Institutions | 2 | 2016 | 193 | 30 | ICTA |  | 0 | 0 | 6 | 24
21 | 76 | Smart Society and Citizen Capacity Building | 3 | 2017 | 154 | 43.73 | ICTA |  | 0 | 0 | 22.7 | 21.03
22 | 75 | Digital Libraries for Knowledge Enhancement | 2 | 2017 | 225 | 23.18 | ICTA |  | 0 | 2.8323 | 5.6998 | 14.65
23 | 36 | e-Heritage Programme - Cutting-edge Technology for Heritage Information | 3 | 2016 | 102.1 | 8.06 | ICTA |  | 0 | 2.395 | 5.1118 | 0.55
24 | 17 | National Security Operations Centre Project | 3 | 2016 | 830.25 | 3 | ICTA |  | 0 | 0 | 1.5 | 1.5
25 | 25 | eGov policy | 3 | 2016 |  | 11.5 | ICTA |  | 0 | 0 | 7.5 | 4
26 | 43 | Web development initiative | 3 | 2016 | 61.5 | 2.27 | ICTA |  | 0 | 0 | 0.53 | 1.74
27 | 82 | eSwabhimani Annual Programme | 3 | 2017 | 30 | 7.8 | ICTA |  | 0 | 0 | 2.35 | 5.45
28 | 79 | Awareness Program (Propaganda) for Digital infrastructure ICTA Initiatives (Strategic Communication) | 3 | 2017 |  | 17.48 | ICTA |  | 0 | 2 | 6 | 9.48
| 49 | ICT in Education sector | 2 | 2016 | 102 | 9.18 | ICTA |  | 0 | 0 | 5.73 | 3.45
Sub Total |  |  |  |  | 13284.94 | 1500 |  | 0 | 0 | 140.6073 | 445.8416 | 913.55
# | NPD Project # | Project Name | Project Duration (Years) | NPD Approved Year | Total Approved Budget (Rs. Mn) | 2018 Planned Budget | Allocation Code | Jan - Apr Invoices (Rs Mn)
MTDI&FE Component
1 | 1 | Lanka Government Network (LGN) 2.0 | 3 | 2016 | 5124.88 | 506 | MTDI
Sub Total |  |  |  |  | 5124.88 | 506
SLCERT Projects
| 18 | National Certification Authority | 3 | 2016 | 289.83 |  | MTDI
| 19 | Enhancement of Cyber Security and Digital Forensic Infrastructure in Sri Lanka CERT¦CC | 3 | 2016 | 49.2 |  | MTDI
| 81 | Security Audits for Government Websites | 2 | 2017 | 89 |  | MTDI
|  | Sub Total |  |  | 428.03 | 0